## Sheet1
Created on | Basic start date | Basic finish date | Order | Order Type | Priority text | System status | User Status | Description | Functional Location | Description of functional location | Total planned costs
2025-03-05 | 2025-04-04 | 2025-06-03 | 80443104 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Replace spinner hatch seal | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 1395.12
2025-03-04 | 2025-03-06 | 2025-03-06 | 80442932 | YR02 | Within 1 month | REL ACAS MSPT PRC | REPL EXSC PPMA | Brake Switch | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 2029.66
2025-03-04 | 2025-03-10 | 2025-04-02 | 80443000 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL | Replace SRL pull down rope | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 1980
2025-03-04 | 2025-03-13 | 2025-04-03 | 80443090 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL | WOW4 ONS -Rob Dale Scopes 13th March | WOW03X01 | Onshore Substation =X01 | 7590
2025-03-03 | 2025-03-06 | 2025-03-06 | 80442574 | YR02 | Immediately | REL ACAS NMAT PRC | RERP EXSC | MSI ExtHighI Info X M 1, L 2 | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 3960
2025-03-03 | 2025-03-07 | 2025-03-30 | 80442967 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Brake release error | WOW03G03MDX | Hydraulic system | 30073.73
2025-03-03 | 2025-03-08 | 2025-03-31 | 80442968 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Missing spinner hatch | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 7087.35
2025-03-03 | 2025-03-08 | 2025-03-31 | 80442969 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Removed entrance to hub hatch blade C | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 8970.25
2025-03-02 | 2025-03-06 | 2025-03-06 | 80442510 | YR02 | Immediately | REL PCNF ACAS MACM PRC | RERP EXSC MATR | BlCEdgeVibration: 246.87 kNm | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 92196.95
2025-03-02 | 2025-03-04 | 2025-03-04 | 80442530 | YR02 | Immediately | REL PCNF ACAS NMAT PRC | RERP | Smoke detected | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 2640
2025-03-02 | 2025-03-03 | 2025-03-03 | 80442531 | YR02 | Within a week | REL PCNF ACAS NMAT PRC | COMP EXSC | Generator Testing | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 7920
2025-03-02 | 2025-02-27 | 2025-02-28 | 80442572 | YR02 | Immediately | REL ACAS NMAT PRC | REPL | Back up Gen fuel leak | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 1980
2025-03-02 | 2025-03-07 | 2025-03-30 | 80442601 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | GearboxBValveCannotClose | WOW03C02MDV | Lubricant system | 41964.37
2025-02-28 | 2025-03-07 | 2025-03-30 | 80442320 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Nacelle Coolant | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 2654.94
2025-02-28 | 2025-03-07 | 2025-03-30 | 80442350 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Nacelle Coolant | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 2654.94
2025-02-27 | 2025-02-24 | 2025-02-25 | 80442157 | YR02 | Immediately | REL ACAS MSPT PRC | REPL | EMF Acc _ Press Low, ___._ bar | WOW03E01MDX | Hydraulic system | 323266.64
2025-02-27 | 2025-02-25 | 2025-02-26 | 80442279 | YR02 | Immediately | REL ACAS MACM PRC | REPL | Smoke detected | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 15601.17
2025-02-27 | 2025-03-03 | 2025-03-03 | 80442280 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP | Lift power cable location | WOW03C03XNM | Lift and Ascent Aid | 1980
2025-02-27 | 2025-03-06 | 2025-03-06 | 80442341 | YR02 | Immediately | REL ACAS MSPT PRC | REPL EXSC PPMA | MSI ExtHighI X Module 1 | WOW03F03MSE | Inverter system | 188044.54
2025-02-20 | 2025-05-19 | 2025-05-25 | 80441413 | YR02 | Immediately | REL PCNF ACAS MACM PRC | RERP | Prop valves unavailable A | WOW03C01MDX | Hydraulic system | 135579.25
2025-02-20 | 2025-02-27 | 2025-02-27 | 80441559 | YR02 | Within a week | REL PCNF ACAS GMPS MACM PRC | RERP | MSI ExtHighI X Module-1 | WOW03C07MSE | Inverter system | 41628.11
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441324 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-02 | 2025-03-02 | 80441325 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441326 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441328 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441329 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441330 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441331 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441333 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-04 | 2025-03-04 | 80441335 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-04 | 2025-03-04 | 80441337 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441338 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441339 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441340 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441341 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441342 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441343 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441344 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441345 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441348 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441349 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-01 | 2025-03-01 | 80441350 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441352 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-04 | 2025-03-04 | 80441353 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record Pitch Ram Serial Numbers | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441354 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441355 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-07 | 2025-03-07 | 80441356 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-06 | 2025-03-06 | 80441357 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-07 | 2025-03-07 | 80441358 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Record Pitch Ram Serial Numbers | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441360 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441361 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441362 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 2640
2025-02-19 | 2025-03-21 | 2025-05-20 | 80441363 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record Pitch Ram Serial Numbers | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 2640
2025-02-18 | 2025-03-11 | 2025-03-17 | 80441071 | YR02 | Immediately | REL ACAS NMAT PRC | REPL | Blade bearing issue. | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 3960
2025-02-18 | 2025-06-23 | 2025-06-29 | 80441192 | YR02 | Within a week | REL ACAS NMAT PRC | REPL | Loose railing on TP | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1980
2025-02-17 | 2025-09-08 | 2025-09-14 | 80440858 | YR02 | Immediately | CRTD ACAS MACM PRC | CRTD | Brake hydraulic leakage high | WOW03D03MDX | Hydraulic system | 13786.26
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440887 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440888 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440889 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440890 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440891 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440892 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440893 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440894 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440895 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440896 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440897 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440898 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440899 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440900 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-05-26 | 2025-06-01 | 80440923 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Potential Oil Leak | WOW03C07MDV | Lubricant system | 7354.08
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440961 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440962 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440963 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440964 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440965 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440966 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440967 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440968 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440969 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440970 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440971 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440972 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440973 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440974 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440975 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440976 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440977 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440978 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440979 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440980 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440981 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440982 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440983 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440984 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440985 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 1320
2025-02-17 | 2025-03-19 | 2026-02-12 | 80440986 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Remove nitrogen bottles from nac | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 1320
2025-02-13 | 2025-03-14 | 2026-02-07 | 80440132 | YR02 | Within a year | REL ACAS MACM PRC | REPL | CMM(2674), V164 Inline Filter GBX Inspec | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 14299.63
2025-02-13 | 2025-07-28 | 2025-08-03 | 80440133 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | CMM(2818), V164HydOilTm | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 22586.08
2025-02-13 | 2025-03-15 | 2025-05-14 | 80440134 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | DynLubrOilLeak M: 929 l | WOW03H03MDV | Lubricant system | 22911.1
2025-02-12 | 2025-03-06 | 2025-03-07 | 80439960 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP EXSC MATR | Blade C blade load sensor replacement | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 128955.03
2025-02-12 | 2025-09-22 | 2025-09-28 | 80439961 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | Tower Emergency Light Battery Brackets | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 16069.28
2025-02-12 | 2025-09-22 | 2025-09-28 | 80439962 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | ABLS Replacement | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 129949.57
2025-02-12 | 2025-03-09 | 2025-05-08 | 80439963 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Aviation light defect | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 67435.5
2025-02-12 | 2025-03-09 | 2025-05-08 | 80439964 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | Main oil tank sightglass | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 2520.15
2025-02-12 | 2025-03-31 | 2025-04-06 | 80439965 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | CMM(2802), V164 Consec. Pitch Block Comm | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 45914.74
2025-02-12 | 2025-03-04 | 2025-03-10 | 80439966 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | HPU fillter needs replacing. | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 5173.38
2025-02-12 | 2025-07-07 | 2025-07-13 | 80439967 | YR02 | Immediately | REL ACAS MACM PRC | REPL | HighIDCLeak | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 67902.31
2025-02-12 | 2025-03-12 | 2026-02-05 | 80439972 | YR02 | Within a year | REL ACAS NMAT PRC | REPL | Rotor lock Perspex cover missing | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 1980
2025-02-12 | 2025-03-12 | 2025-05-11 | 80439973 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | Cracked F bracket blade C down left door | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 6293.66
2025-02-12 | 2025-03-13 | 2025-05-12 | 80439977 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 16945.7
2025-02-12 | 2025-03-13 | 2025-05-12 | 80439978 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 16945.7
2025-02-12 | 2025-03-07 | 2025-03-07 | 80439979 | YR02 | Immediately | REL ACAS MACM PRC | REPL EXSC | Lift bracket broken PCM 4 | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 4096.88
2025-02-12 | 2025-03-13 | 2025-05-12 | 80439980 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | DynLubrOilLeak M: 948 l | WOW03D03MDV | Lubricant system | 12445.55
2025-02-11 | 2025-04-01 | 2025-04-07 | 80439926 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | High IDC and smoke inspection | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 46213.48
2025-02-11 | 2025-03-04 | 2025-03-10 | 80439956 | YR02 | Immediately | REL ACAS MACM PRC | REPL | Roto guard missing | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 839.23
2025-02-09 | 2025-03-11 | 2025-05-10 | 80439625 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 79558.61
2025-02-09 | 2025-09-01 | 2025-09-07 | 80439626 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | Smoke detected | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 15601.17
2025-02-09 | 2025-03-11 | 2025-05-10 | 80439627 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | DynLubrOilLeak M:1056 l | WOW03H03MDV | Lubricant system | 16971.1
2025-02-07 | 2025-05-12 | 2025-05-18 | 80439248 | YR02 | Within a week | REL PCNF ACAS MACM PRC | RERP EXSC | No communication to WTG (single) | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 8568.78
2025-02-03 | 2025-05-12 | 2025-05-18 | 80437829 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | Pump/motor | WOW03B02MDX01GP003 | Motor Pump 3 Assy 50 Hz (Pos 16) | 49270.01
2025-01-31 | 2025-05-12 | 2025-05-18 | 80437278 | YR02 | Within a year | REL ACAS NMAT PRC | REPL | Nacelle telescopic ladder missing. | WOW03B02XNM | Lift and Ascent Aid | 1980
2025-01-30 | 2025-04-01 | 2025-04-07 | 80437079 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | CMM(2802), V164 Consec. Pitch Block Comm | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 33746.94
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436153 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP EXSC | Hole in nacelle and hub fibre | WOW03B03MUD50 | Nacelle cover | 5280
2025-01-23 | 2025-09-08 | 2025-09-14 | 80436203 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | H02 Needle Valve Handles | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 3677.82
2025-01-23 | 2025-09-08 | 2025-09-14 | 80436204 | YR02 | Within a week | CRTD ACAS MACM PRC | CRTD | LCTU Nacelle side arm damaged | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 10170.3
2025-01-23 | 2025-09-08 | 2025-09-14 | 80436205 | YR02 | Within a week | CRTD ACAS MACM PRC | CRTD | Hub Entry Hatch Seals | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 735.12
2025-01-23 | 2025-06-23 | 2025-06-29 | 80436207 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 79074.12
2025-01-23 | 2025-06-30 | 2025-07-06 | 80436210 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | H01 Nacelle light replacement | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 1320.07
2025-01-23 | 2025-06-30 | 2025-07-06 | 80436270 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Wow03 D02 tetra comms | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 2640
2025-01-23 | 2025-06-23 | 2025-06-29 | 80436330 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436332 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-04-28 | 2025-05-04 | 80436335 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436337 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436339 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Remove all Blade Root Hatches | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-04 | 2025-03-04 | 80436341 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Remove all Blade Root Hatches | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-04 | 2025-03-04 | 80436343 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Remove all Blade Root Hatches | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-08-18 | 2025-08-24 | 80436344 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-06-16 | 2025-06-22 | 80436345 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-06-16 | 2025-06-22 | 80436347 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436348 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-02-25 | 2025-02-25 | 80436351 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Remove all Blade Root Hatches | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-02 | 2025-03-02 | 80436352 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | COMP EXSC | Remove all Blade Root Hatches | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-07-07 | 2025-07-13 | 80436354 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436355 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-10-06 | 2025-10-12 | 80436360 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-08-25 | 2025-08-31 | 80436361 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Remove all Blade Root Hatches | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-07 | 2025-03-07 | 80436362 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-06 | 2025-03-06 | 80436363 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 7920
2025-01-23 | 2025-03-07 | 2025-03-07 | 80436364 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP EXSC | Remove all Blade Root Hatches | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 7920
2025-01-20 | 2025-09-22 | 2025-09-28 | 80435802 | YR02 | Within a year | REL ACAS NMAT PRC | REPL | LSI filter side panel bolts rounded . | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 1980
2025-01-20 | 2025-05-05 | 2025-05-11 | 80435804 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | CMM(2672), V164 Nac Open Breather Leak I | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 8582.12
2025-01-20 | 2025-02-25 | 2025-03-03 | 80435805 | YR02 | Within a year | REL ACAS NMAT PRC | REPL | No extendable ladders on turbine | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 1980
2025-01-20 | 2025-05-05 | 2025-05-11 | 80435806 | YR02 | Within 1 month | REL ACAS MACM PRC | REPL | HPU Brake accumulator leak | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 10174.1
2025-01-20 | 2025-03-06 | 2025-03-06 | 80435817 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | Nacelle Coolant | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 4676.6
2025-01-20 | 2025-06-09 | 2025-06-15 | 80435878 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Hatch Investigation | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 3960
2025-01-20 | 2025-05-19 | 2025-05-25 | 80435879 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP | Fog Signal Checks | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 1980
2025-01-20 | 2025-08-18 | 2025-08-24 | 80435883 | YR02 | Within a week | REL ACAS NMAT PRC | RERP | Scrap metal and bottles in nacelle | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 1980
2025-01-17 | 2025-05-26 | 2025-06-01 | 80434867 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | Wow03 c07 Rounded nut on pump 3 filter | WOW03C07MDX01GP003 | Motor Pump 3 Assy 50 Hz (Pos 16) | 11534.04
2025-01-17 | 2025-09-08 | 2025-09-14 | 80434868 | YR02 | Immediately | REL ACAS NMAT PRC | RERP | Pwr backup battery bank err | WOW03H02MDY | Control and protection System | 3960
2025-01-13 | 2025-07-28 | 2025-08-03 | 80434159 | YR02 | Immediately | REL ACAS MACM PRC | RERP | MSI HW Err Info Y Module 2,L 3 | WOW03H03MSE | Inverter system | 31942.34
2025-01-12 | 2025-07-07 | 2025-07-13 | 80434148 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Replace cracked brackets and anchor p's | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 30314.46
2025-01-11 | 2025-09-08 | 2025-09-14 | 80434083 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Lift broken | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 5280
2025-01-11 | 2025-03-07 | 2025-03-07 | 80434084 | YR02 | Within a year | REL ACAS MACM PRC | REPL EXSC | 3x lift brackets broke | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 1646.56
2025-01-10 | 2025-07-28 | 2025-08-03 | 80433756 | YR02 | Within 1 month | REL ACAS GMPS MACM PRC | RERP EXSC MATR | Nacelle coolant level | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 8581.92
2025-01-10 | 2025-07-28 | 2025-08-03 | 80433771 | YR02 | Within a week | CRTD ACAS MACM PRC | CRTD | H03 Front Door won’t lock | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 5125.86
2025-01-10 | 2025-05-05 | 2025-05-11 | 80433805 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Hydraulic Pump 3 left open | WOW03C03MDX01GP003 | Motor Pump 3 Assy 50 Hz (Pos 16) | 48296.12
2025-01-10 | 2025-06-09 | 2025-06-15 | 80433853 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | F02 Replace Back-up Generator Battery | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 4057.79
2025-01-10 | 2025-07-28 | 2025-08-03 | 80433938 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | replacement generator bearing cassette | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 0
2025-01-08 | 2025-03-04 | 2025-03-04 | 80432760 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Record serial numbers of pitch cylinders | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 1320
2025-01-08 | 2025-04-14 | 2025-04-20 | 80432785 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record serial numbers of pitch cylinders | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 1320
2025-01-08 | 2025-03-04 | 2025-03-04 | 80432801 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Record serial numbers of pitch cylinders | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 1320
2025-01-08 | 2025-06-16 | 2025-06-22 | 80432803 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Record serial numbers of pitch cylinders | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 1320
2025-01-07 | 2025-09-22 | 2025-09-28 | 80432512 | YR02 | Within 1 month | REL ACAS GMPS PRC | RERP | CMM(2672), V164 Nac Open Breather Leak I | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 7920
2025-01-07 | 2025-09-08 | 2025-09-14 | 80432517 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | LCTU bracket cracked | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 1980
2025-01-04 | 2025-04-14 | 2025-04-20 | 80432105 | YR02 | Within a year | REL ACAS MACM PRC | REPL | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 16959.17
2025-01-04 | 2025-09-29 | 2025-10-05 | 80432106 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 16959.17
2025-01-04 | 2025-04-14 | 2025-04-20 | 80432107 | YR02 | Within a year | REL ACAS MACM PRC | REPL | *STATS* Avanti service lift | WOW03A02XNM70GM001 | Service Lift Installation | 4246.92
2025-01-02 | 2025-10-06 | 2025-10-12 | 80431913 | YR02 | Immediately | REL ACAS PRC | RERP | DynLubrOilLeak M:1089 l | WOW03F05MDV | Lubricant system | 3960
2024-12-30 | 2025-09-08 | 2025-09-14 | 80431711 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 16945.7
2024-12-30 | 2025-06-30 | 2025-07-06 | 80431712 | YR02 | Within 3 months | CRTD ACAS MSPT PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 16959.17
2024-12-28 | 2025-04-21 | 2025-04-27 | 80431362 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Re-fit yaw skirt and nacelle hatch seal | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 5280
2024-12-27 | 2025-06-16 | 2025-06-22 | 80431321 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Hub CMS Ethernet cable damaged | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 660
2024-12-26 | 2025-07-07 | 2025-07-13 | 80431140 | YR02 | Within a year | CRTD ACAS MSPT PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 16979.28
2024-12-26 | 2025-03-04 | 2025-03-10 | 80431163 | YR02 | Within a week | REL PCNF ACAS MACM PRC | RERP | Prop valve unavailable blade B | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 11919.03
2024-12-26 | 2025-07-07 | 2025-07-13 | 80431181 | YR02 | Within 3 months | CRTD ACAS MSPT PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 16979.28
2024-12-26 | 2025-09-01 | 2025-09-07 | 80431241 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | CMM(2810), Hub Accumulator Capacity Insp | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 44041.63
2024-12-26 | 2025-06-30 | 2025-07-06 | 80431242 | YR02 | Within 3 months | CRTD ACAS MSPT PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 16979.28
2024-12-26 | 2025-09-08 | 2025-09-14 | 80431243 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 16959.17
2024-12-21 | 2025-09-08 | 2025-09-14 | 80430850 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2779), V164 De-Rate Code 36 Insp. Re | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 123328.36
2024-12-17 | 2025-06-23 | 2025-06-29 | 80430212 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 16946.94
2024-12-17 | 2025-08-18 | 2025-08-24 | 80430278 | YR02 | Within 1 month | REL ACAS GMPS MACM PRC | RERP | Rotating union hydraulic oil leak | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 9352.44
2024-12-16 | 2025-05-19 | 2025-05-25 | 80429997 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | Spinner bracket cracked | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 7570.1
2024-12-16 | 2025-09-29 | 2025-10-05 | 80430203 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Hub clean up | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 5280
2024-12-14 | 2025-05-12 | 2025-05-18 | 80429739 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | TCM(b), M-System | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 150950.71
2024-12-13 | 2025-07-07 | 2025-07-13 | 80429636 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | CMM(2791), V164 De-Rate Code 48 Insp. Re | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 5280
2024-12-13 | 2025-06-09 | 2025-06-15 | 80429712 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 22701.06
2024-12-13 | 2025-04-21 | 2025-04-27 | 80429713 | YR02 | Within 3 months | REL ACAS MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 22316
2024-12-13 | 2025-04-14 | 2025-04-20 | 80429714 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 22316
2024-12-13 | 2025-04-07 | 2025-04-13 | 80429725 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2808), V164 Consec. GenSide Brkr Ins | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 74258.31
2024-12-13 | 2025-07-21 | 2025-07-27 | 80429726 | YR02 | Within a week | CRTD ACAS MACM PRC | CRTD | TCM(a), M-System | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 150950.71
2024-12-13 | 2025-04-28 | 2025-05-04 | 80429750 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 16959.17
2024-12-13 | 2025-04-07 | 2025-04-13 | 80429751 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 22316
2024-12-11 | 2025-05-12 | 2025-05-18 | 80429551 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Tetra radio repeater troubleshoot | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 5280
2024-12-10 | 2025-02-25 | 2025-03-03 | 80429431 | YR02 | Within a week | REL ACAS CSER NMAT PRC | REPL | BoP (Class 2) WOW03Z03AAF24 | WOW03Z03AAF24 | 34kV System - String 9 | 0
2024-12-08 | 2025-08-18 | 2025-08-24 | 80429268 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP EXSC MATR | Swapping core cables | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 6429.63
2024-12-08 | 2025-07-28 | 2025-08-03 | 80429273 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2920), Wind Sensor Misalign.Insp. Re | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 21170.73
2024-12-03 | 2025-06-23 | 2025-06-29 | 80428598 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Spinner support stanchion bolts retro | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 3960
2024-12-03 | 2025-03-24 | 2025-03-30 | 80428599 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | Nav light to be checked | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 16903.54
2024-12-02 | 2025-09-22 | 2025-09-28 | 80428206 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | CMM(2920), Wind Sensor Misalign.Insp. Re | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 15230.73
2024-11-29 | 2025-09-29 | 2025-10-05 | 80428013 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | HMI screen fault | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 11162.46
2024-11-29 | 2025-06-02 | 2025-06-08 | 80428023 | YR02 | Immediately | CRTD ACAS CSER MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 14396
2024-11-29 | 2025-06-09 | 2025-06-15 | 80428041 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | CMM(2810), Hub Accumulator Capacity Insp | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 44041.63
2024-11-29 | 2025-08-18 | 2025-08-24 | 80428042 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | CMM(2810), Hub Accumulator Capacity Insp | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 44040.91
2024-11-29 | 2025-09-22 | 2025-09-28 | 80428062 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Guide wire bracket pcm4 | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 705.69
2024-11-28 | 2025-07-28 | 2025-08-03 | 80427650 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | CMM(2779), V164 De-Rate Code 36 Insp. Re | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 135862.12
2024-11-28 | 2025-05-19 | 2025-05-25 | 80427658 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | Loose connection slip ring | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 47361.68
2024-11-27 | 2025-06-23 | 2025-06-29 | 80427594 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Faulty accumulator | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 11419.85
2024-11-27 | 2025-09-22 | 2025-09-28 | 80427642 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Back up gen coolant pipe perished. | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 1320
2024-11-26 | 2025-07-28 | 2025-08-03 | 80427458 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | Turbine Lights | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 3431.74
2024-11-21 | 2025-04-07 | 2025-04-13 | 80426842 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | CMM(2920), Wind Sensor Misalign.Insp. Re | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 17121.32
2024-11-19 | 2025-04-07 | 2025-04-13 | 80426571 | YR02 | Immediately | REL PCNF ACAS MSPT PRC | RERP | EMFAccuPressLow: Blade 1 | WOW03B04MDX | Hydraulic system | 36916.37
2024-11-19 | 2025-02-25 | 2025-03-03 | 80426644 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL MATR | SCADA WOW04 AVINAVI server | WOW03X01 | Onshore Substation =X01 | 758.53
2024-11-19 | 2025-02-25 | 2025-03-03 | 80426645 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | SCADA WOW04 HPPP1_2 server | WOW03X01 | Onshore Substation =X01 | 2674.96
2024-11-16 | 2025-04-07 | 2025-04-13 | 80426210 | YR02 | Immediately | REL ACAS MACM PRC | RERP | MSI InvCurrentLoadShare | WOW03B04MSE | Inverter system | 13520.57
2024-11-16 | 2025-07-28 | 2025-08-03 | 80426230 | YR02 | Immediately | REL PCNF ACAS CSER GMPS MACM PRC | RERP | Smoke detected | WOW03F05MDY | Control and protection System | 21885.03
2024-11-15 | 2025-05-26 | 2025-06-01 | 80426193 | YR02 | Immediately | CRTD ACAS CSER MACM PRC | CRTD | Davit hoist wire lowers approx 30cm only | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 25399.62
2024-11-15 | 2025-04-14 | 2025-04-20 | 80426221 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Replace spinner stantions and bolts | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 0
2024-11-14 | 2025-07-28 | 2025-08-03 | 80426022 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | HMF crane repair | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 68424.84
2024-11-13 | 2025-04-14 | 2025-04-20 | 80425817 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | Smoke Detector Sensor Soiled | WOW03A02MDY | Control and protection System | 12921.77
2024-11-13 | 2025-04-21 | 2025-04-27 | 80425888 | YR02 | Within a week | REL PCNF ACAS GMPS MACM PRC | RERP | Smoke Detector Sensor Error | WOW03B03MDY | Control and protection System | 3113.27
2024-11-11 | 2025-06-30 | 2025-07-06 | 80425589 | YR02 | Within a week | REL ACAS CSER MACM PRC | REPL | TCM(a), M-System | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 149630.71
2024-11-09 | 2025-03-03 | 2025-03-03 | 80425360 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Poor operation of Nacelle crane. | WOW03B03XMM50GM001-GM001 | Crane, gear | 1980
2024-11-08 | 2025-09-22 | 2025-09-28 | 80425345 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Munchers dehumidifier | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 15693.72
2024-11-08 | 2025-04-07 | 2025-04-13 | 80425346 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL | Backup gen low fuel | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 1980
2024-11-08 | 2025-04-21 | 2025-04-27 | 80425347 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | Nacelle roof Hydraulic leak | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 2025.39
2024-11-07 | 2025-03-24 | 2025-03-30 | 80425074 | YR02 | Within a week | REL PCNF ACAS MACM PRC | RERP | TCM(a), M-System Hub | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 44374.54
2024-11-05 | 2025-03-24 | 2025-03-30 | 80424907 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Avanti lift bottom stop bracket broken | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 0
2024-11-05 | 2025-05-26 | 2025-06-01 | 80424947 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | 3 x old pitch cylinders left on TP | WOW03H02Z | Structure and areas outside PP Process | 0
2024-11-04 | 2025-04-28 | 2025-05-04 | 80424536 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2808), V164 Consec. GenSide Brkr Ins | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 74211.91
2024-11-04 | 2025-05-12 | 2025-05-18 | 80424587 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Blade Load Sensor Fault | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 110029.07
2024-11-03 | 2025-04-07 | 2025-04-13 | 80424498 | YR02 | Immediately | REL ACAS NMAT PRC | RERP | Pin missing from manual pitch lock | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 660
2024-11-03 | 2025-07-07 | 2025-07-13 | 80424525 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 79074.12
2024-11-03 | 2025-04-07 | 2025-04-13 | 80424526 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | TCM(a), M-System | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 662.6
2024-11-03 | 2025-04-21 | 2025-04-27 | 80424544 | YR02 | Within a week | REL ACAS CSER MACM PRC | REPL | B03 HPU motor 2 not working. | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 32653.43
2024-11-02 | 2025-06-02 | 2025-06-08 | 80424390 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Backup gen waste oil pump faulty | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 0
2024-11-01 | 2025-07-28 | 2025-08-03 | 80424305 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Backup gen waste oil pump faulty | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 0
2024-11-01 | 2025-05-19 | 2025-05-25 | 80424306 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Backup gen coolant heater | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 2424.39
2024-11-01 | 2025-07-28 | 2025-08-03 | 80424307 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Backup gen coolant heater faulty | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 2424.39
2024-10-31 | 2025-03-31 | 2025-04-06 | 80424142 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wow03 A04 Back up gen heater | WOW03A04BRA01FC075 | Generator backup | 2424.39
2024-10-31 | 2025-05-19 | 2025-05-25 | 80424143 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Back up gen hot coolant heater | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 2424.39
2024-10-31 | 2025-05-26 | 2025-06-01 | 80424146 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Replace GearboxA1A2OilSumpTemp sensor | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 521.47
2024-10-31 | 2025-04-21 | 2025-04-27 | 80424174 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Slow nacelle crane | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 0
2024-10-30 | 2025-05-05 | 2025-05-11 | 80423933 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | F04 backup gen service outstanding tasks | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 2424.39
2024-10-29 | 2025-08-18 | 2025-08-24 | 80423740 | YR02 | Immediately | REL ACAS MACM PRC | RERP | DynLubrOilLeak M:1056 l | WOW03C06MDV | Lubricant system | 12445.55
2024-10-28 | 2025-09-22 | 2025-09-28 | 80423697 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | False “Spring not Charged” alarm | WOW03F04AFA70WA001-QA001 | CBP breaker | 1980
2024-10-28 | 2025-05-19 | 2025-05-25 | 80423738 | YR02 | Immediately | REL ACAS CSER MACM PRC | REPL | STATS: Service lift out of use | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 313.57
2024-10-27 | 2025-09-08 | 2025-09-14 | 80423576 | YR02 | Within a week | REL PCNF ACAS PRC | RERP | Pwr backup battery bank err | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 5280
2024-10-24 | 2025-05-12 | 2025-05-18 | 80423178 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP EXSC | Toilet on Turbine Sticker | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-05-19 | 2025-05-25 | 80423222 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-03-03 | 2025-03-03 | 80423223 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-05-26 | 2025-06-01 | 80423225 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-06-16 | 2025-06-22 | 80423227 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-06-16 | 2025-06-22 | 80423229 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-04-14 | 2025-04-20 | 80423230 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-09-08 | 2025-09-14 | 80423231 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-03-03 | 2025-03-03 | 80423234 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-03-02 | 2025-03-02 | 80423235 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-04-21 | 2025-04-27 | 80423262 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-06-02 | 2025-06-08 | 80423265 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-03-06 | 2025-03-06 | 80423266 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Toilet on Turbine Sticker | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-06-30 | 2025-07-06 | 80423267 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-06-02 | 2025-06-08 | 80423269 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 660
2024-10-24 | 2025-04-07 | 2025-04-13 | 80423270 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 0
2024-10-24 | 2025-07-07 | 2025-07-13 | 80423271 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Toilet on Turbine Sticker | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 660
2024-10-23 | 2025-04-14 | 2025-04-20 | 80422488 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Check DC Cables | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 0
2024-10-23 | 2025-04-14 | 2025-04-20 | 80422489 | YR02 | Within 1 month | REL PCNF ACAS CSER NMAT PRC | RERP | Check DC cables | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 0
2024-10-22 | 2025-09-08 | 2025-09-14 | 80422392 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Antifoam additive required | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 1320
2024-10-22 | 2025-09-22 | 2025-09-28 | 80422432 | YR02 | Within a year | REL ACAS MACM PRC | RERP | CMM(2674), V164 Inline Filter GBX Inspec | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 13908.3
2024-10-21 | 2025-04-07 | 2025-04-13 | 80421796 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP | Nacelle coolant leak | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 8582.12
2024-10-18 | 2025-06-16 | 2025-06-22 | 80421072 | YR02 | Immediately | REL PCNF ACAS GMPS MACM PRC | RERP EXSC MATR | EMFAccuPressLow: Blade 1 | WOW03B02MDX | Hydraulic system | 4192.48
2024-10-18 | 2025-09-08 | 2025-09-14 | 80421076 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | CMM(2818), V164HydOilTm | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 20404.22
2024-10-17 | 2025-02-25 | 2025-03-03 | 80420745 | YR02 | Within a week | REL ACAS CSER NMAT PRC | REPL | BoP (Class 2) WOW03Z03AAF11 | WOW03Z03AAF11 | 34kV System - String 2 | 0
2024-10-17 | 2025-04-07 | 2025-04-13 | 80420820 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Smoke Detector Sensor Soiled | WOW03H04MDY | Control and protection System | 473.27
2024-10-17 | 2025-07-28 | 2025-08-03 | 80421021 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Smoke Detector Sensor Soiled | WOW03G02MDY | Control and protection System | 3113.27
2024-10-16 | 2025-05-26 | 2025-06-01 | 80420670 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Nacelle craning hatch missing stake | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2024-10-16 | 2025-06-23 | 2025-06-29 | 80420707 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | REPL | AFA70 Switchgear Circuit breaker | WOW03D05AAF80WA001 | Switch gear installation | 0
2024-10-15 | 2025-04-21 | 2025-04-27 | 80420559 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | REPL | Rotor lock lever manifold damaged | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 0
2024-10-15 | 2025-04-07 | 2025-04-13 | 80420625 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | Hub cabinet heating not working | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 782.22
2024-10-15 | 2025-09-08 | 2025-09-14 | 80420626 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | RCCB test not working | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 2274.81
2024-10-15 | 2025-05-19 | 2025-05-25 | 80420627 | YR02 | Within a year | REL ACAS CSER MACM PRC | REPL | Filter housing removal. | WOW03C01MDV01HQ002 | Inline filtration generator/main bearing | 8350.52
2024-10-14 | 2025-04-07 | 2025-04-13 | 80420350 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Yaw cable damage | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 0
2024-10-12 | 2025-08-18 | 2025-08-24 | 80420285 | YR02 | Within 1 month | REL ACAS PRC | RERP | Blade Movement | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 3960
2024-10-11 | 2025-06-30 | 2025-07-06 | 80420178 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | TCM(b), GbxA1Pln3-R | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 44374.54
2024-10-11 | 2025-05-12 | 2025-05-18 | 80420179 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | TCM(b), Sensor cables | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 42513.3
2024-10-11 | 2025-07-28 | 2025-08-03 | 80420180 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(b), Oil debris sensors | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 44191.54
2024-10-09 | 2025-08-25 | 2025-08-31 | 80420037 | YR02 | Within a week | REL ACAS MACM PRC | RERP | Davit- slack cable wire bracket damaged | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 9483.38
2024-10-08 | 2025-05-19 | 2025-05-25 | 80419768 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | No lighting at top lift level | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 151.78
2024-10-08 | 2025-06-16 | 2025-06-22 | 80419769 | YR02 | Immediately | CRTD ACAS CSER MACM PRC | CRTD | PitchBlockPilotPressLow 192bar | WOW03H04MDX | Hydraulic system | 354.5
2024-10-07 | 2025-09-01 | 2025-09-07 | 80419656 | YR02 | Within 1 month | REL ACAS GMPS NMAT PRC | REPL | Carry out remaining STATS | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 5940
2024-10-06 | 2025-06-09 | 2025-06-15 | 80419530 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | PCM guide bracket snapped | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 1365.69
2024-10-04 | 2025-09-01 | 2025-09-07 | 80419295 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | TP First aid inspection date expired | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 622.6
2024-10-04 | 2025-05-26 | 2025-06-01 | 80419308 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Found loose boltsleft side nacelle panel | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2024-10-04 | 2025-03-24 | 2025-03-30 | 80419385 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Wow03 a03 hub safe switch damaged | WOW03A03XSP60 | Personal Safety Equipment, Nacelle/YAW | 49.43
2024-10-01 | 2025-04-07 | 2025-04-13 | 80419133 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Spinner hatch missing | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 5107.14
2024-10-01 | 2025-05-26 | 2025-06-01 | 80419135 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | REPL | Nacelle crane umbilical | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 408.98
2024-09-27 | 2025-06-09 | 2025-06-15 | 80418744 | YR02 | Within a week | REL ACAS GMPS MACM PRC | RERP | Smoke Detector Sensor Soiled | WOW03G01MDY | Control and protection System | 3122.58
2024-09-26 | 2025-09-08 | 2025-09-14 | 80418679 | YR02 | Within a week | REL ACAS MACM PRC | RERP | Smoke Detector Sensor Soiled | WOW03G03MDY | Control and protection System | 3122.58
2024-09-24 | 2025-05-26 | 2025-06-01 | 80418460 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | Damaged HMF crane remote cable | WOW03C04XM | Crane assemblies, stationary hoists | 408.98
2024-09-24 | 2025-06-02 | 2025-06-08 | 80418515 | YR02 | Within 3 months | REL PCNF ACAS CSER MACM PRC | RERP | Cracked spinner support brackets | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 9565.84
2024-09-24 | 2025-06-02 | 2025-06-08 | 80418516 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Missing M10 screw and retaining plate | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 249.62
2024-09-24 | 2025-09-22 | 2025-09-28 | 80418524 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | PCM4 cac unit leaking | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 2305.68
2024-09-24 | 2025-02-28 | 2025-02-28 | 80418525 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Smoke test | WOW03E02CKA02 | Fire detection Advanced | 2389.24
2024-09-24 | 2025-06-02 | 2025-06-08 | 80418526 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | TCM(b), GbxA1Pln1-T | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 42722.97
2024-09-23 | 2025-03-24 | 2025-03-30 | 80418181 | YR02 | Within a year | CRTD ACAS NMAT PRC | REPL | Sea Sight Davit Elec. Cabinet Insp. | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 660
2024-09-23 | 2025-04-28 | 2025-05-04 | 80418184 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Sea Sight Davit Elec. Cabinet Insp. | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-06-09 | 2025-06-15 | 80418190 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Sea Sight Davit Elec. Cabinet Insp. | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 660
2024-09-23 | 2025-05-26 | 2025-06-01 | 80418192 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | REPL | Sea Sight Davit Elec. Cabinet Insp. | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-04-14 | 2025-04-20 | 80418197 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | REPL | Sea Sight Davit Elec. Cabinet Insp. | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-05-19 | 2025-05-25 | 80418202 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | REPL | Sea Sight Davit Elec. Cabinet Insp. | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-09-01 | 2025-09-07 | 80418206 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Sea Sight Davit Elec. Cabinet Insp. | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-04-07 | 2025-04-13 | 80418218 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | REPL | Sea Sight Davit Elec. Cabinet Insp. | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 0
2024-09-23 | 2025-07-07 | 2025-07-13 | 80418219 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Sea Sight Davit Elec. Cabinet Insp. | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 660
2024-09-22 | 2025-04-14 | 2025-04-20 | 80417824 | YR02 | Immediately | REL ACAS CSER MACM PRC | RERP | Replace PSU | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 4599.74
2024-09-21 | 2025-04-14 | 2025-04-20 | 80417821 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | TP Lights not working. | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 0
2024-09-20 | 2025-05-12 | 2025-05-18 | 80417660 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Brackets and bolts missing | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 928.26
2024-09-17 | 2025-03-31 | 2025-04-06 | 80417138 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 95583.56
2024-09-16 | 2025-03-31 | 2025-04-06 | 80416963 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | Cisco card removed taken to F05. | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 0
2024-09-16 | 2025-05-05 | 2025-05-11 | 80416966 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | REPL | Hub lights plug requires replacement | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 113.29
2024-09-16 | 2025-07-28 | 2025-08-03 | 80417036 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | CMM(2817), V164 Warning Time-Out Insp. R | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 0
2024-09-16 | 2025-02-25 | 2025-03-03 | 80417042 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | CMM(2818), V164HydOilTm | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 37609.1
2024-09-14 | 2025-06-16 | 2025-06-22 | 80416855 | YR02 | Within a week | REL ACAS MACM PRC | RERP | Smoke Detector Sensor Soiled | WOW03D01MDY | Control and protection System | 3113.27
2024-09-12 | 2025-03-31 | 2025-04-06 | 80416702 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | CMM(2817), V164 Warning Time-Out Insp. R | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 473.27
2024-09-11 | 2025-05-05 | 2025-05-11 | 80416649 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Transformer coolant pump service | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 0
2024-09-10 | 2025-05-05 | 2025-05-11 | 80416544 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Transformer coolant pump leak | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 0
2024-09-07 | 2025-02-27 | 2025-02-27 | 80416151 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | (Service) Unable to do over speed test | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 2640
2024-09-07 | 2025-06-09 | 2025-06-15 | 80416191 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Hydraulic hose supply to RTU. | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 212.8
2024-09-07 | 2025-06-16 | 2025-06-22 | 80416192 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | C06, blade hatch handle | WOW03C06MDA10 | Rotor & Hub Structure | 0
2024-09-07 | 2025-09-01 | 2025-09-07 | 80416193 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Yaw motor error | WOW03F02MDL | Yaw system | 38212.02
2024-09-07 | 2025-03-31 | 2025-04-06 | 80416194 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | *STATS* Avanti lift interlock | WOW03D01XN | Elevator System | 0
2024-09-07 | 2025-04-07 | 2025-04-13 | 80416195 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | Roof locking pin assembly | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 173.21
2024-09-06 | 2025-05-19 | 2025-05-25 | 80416013 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Switchgear control local/remote switch | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 5280
2024-09-06 | 2025-05-05 | 2025-05-11 | 80416014 | YR02 | Within a week | CRTD ACAS MACM PRC | CRTD | EMF Acc 1 Press Low, 209.4 bar | WOW03F04MDX | Hydraulic system | 311912.54
2024-09-06 | 2025-05-19 | 2025-05-25 | 80416015 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Nacelle crane hatch rope snapped | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-09-06 | 2025-05-19 | 2025-05-25 | 80416016 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Backup generator coolant leak | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-09-06 | 2025-04-21 | 2025-04-27 | 80416017 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | WOW03 B03 main TP Gate damaged | WOW03B03UMD80 | Transition Piece_TP | 0
2024-09-06 | 2025-04-14 | 2025-04-20 | 80416019 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | LSI ExtHighI Y Module-1 | WOW03E01MSE | Inverter system | 209430.53
2024-09-06 | 2025-09-22 | 2025-09-28 | 80416020 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Missing grating from accumulators on all | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 0
2024-09-06 | 2025-06-09 | 2025-06-15 | 80416081 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | C05, hub in service mode issue | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 0
2024-09-05 | 2025-06-02 | 2025-06-08 | 80415946 | YR02 | Within 3 months | REL ACAS CSER PRC | RERP | Hydraulic ram on roof | WOW03H03UMD75 | Structure overall | 0
2024-09-05 | 2025-07-07 | 2025-07-13 | 80415948 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Coolant and oil under generator | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 3960
2024-09-05 | 2025-04-21 | 2025-04-27 | 80415949 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | =BFB71FC001-FC006 Breaker damaged | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2024-09-05 | 2025-06-09 | 2025-06-15 | 80415951 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 13451.52
2024-09-03 | 2025-05-19 | 2025-05-25 | 80413276 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | GearFiltPressTooHigh 3.3bar | WOW03C01MDV | Lubricant system | 1689.94
2024-09-03 | 2025-05-19 | 2025-05-25 | 80414145 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | AFA 70 panel cover stuck | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-09-02 | 2025-05-12 | 2025-05-18 | 80413548 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Hmf nacelle crane slow slew | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 0
2024-09-01 | 2025-06-30 | 2025-07-06 | 80412522 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Turner Gear Pendent only works one way. | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 0
2024-08-31 | 2025-06-30 | 2025-07-06 | 80412438 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | CMM(2818), V164HydOilTm | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 9701.9
2024-08-29 | 2025-06-09 | 2025-06-15 | 80412304 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | WOW03 C02 Toilet on Turbine | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 1320
2024-08-27 | 2025-04-07 | 2025-04-13 | 80412072 | YR02 | Within a week | REL ACAS CSER MACM PRC | RERP | Pitch C BL unlock alarm N= 21 | WOW03H04MDY | Control and protection System | 17423.24
2024-08-26 | 2025-03-31 | 2025-04-06 | 80411832 | YR02 | Within 3 months | REL PCNF ACAS CSER GMPS MACM PRC | RERP | CMM(2801), V164 Gear Oil Level Insp. Req | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 9064.38
2024-08-23 | 2025-05-19 | 2025-05-25 | 80411367 | YR02 | Within a year | REL PCNF ACAS CSER MACM PRC | RERP | Hyd Oil Clean Up | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 3042.48
2024-08-22 | 2025-03-10 | 2025-03-16 | 80411013 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | TCM(b), Oil debris sensor GEN | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 42026.23
2024-08-22 | 2025-06-23 | 2025-06-29 | 80411017 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP EXSC | SF6 alarm not registering in Scada. | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 0
2024-08-22 | 2025-08-18 | 2025-08-24 | 80411266 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP EXSC MATR | Damage found to Nav aid number 2. | WOW03F01XSD81 | Navigation marine aids signalling - TP | 85045.06
2024-08-19 | 2025-09-22 | 2025-09-28 | 80410462 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(a), M-System | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 152737.68
2024-08-17 | 2025-04-21 | 2025-04-27 | 80410136 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Damaged Seasight Davit cowling | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 3815.38
2024-08-17 | 2025-04-21 | 2025-04-27 | 80410254 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Smoke Detector Sensor Soiled | WOW03B03MDY | Control and protection System | 3605.16
2024-08-15 | 2025-06-02 | 2025-06-08 | 80410028 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Aviation Equipment Error | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 73652.06
2024-08-15 | 2025-04-21 | 2025-04-27 | 80410091 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Aviation Equipment Error | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 73652.06
2024-08-14 | 2025-08-18 | 2025-08-24 | 80409877 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Aviation light supply incorrect | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 660
2024-08-14 | 2025-07-07 | 2025-07-13 | 80409879 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(b), M-System | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 76277.11
2024-08-14 | 2025-06-30 | 2025-07-06 | 80410002 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | WOW03 H01 slip ring | WOW03H01MDA10UL001 | Rotor Hub Installation | 45543.45
2024-08-08 | 2025-02-25 | 2025-03-03 | 80409174 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL | Starlink Install WOW3/4 ONSS: Rob Dale | WOW03X01 | Onshore Substation =X01 | 7590
2024-08-08 | 2025-06-23 | 2025-06-29 | 80409222 | YR02 | Immediately | REL ACAS CSER NMAT PRC | REPL | WOW03 Stat Boat Stock Consumption | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 0
2024-08-07 | 2025-04-14 | 2025-04-20 | 80409164 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Tower coolant leak | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 0
2024-08-06 | 2025-03-04 | 2025-03-04 | 80401248 | YR02 | Within a week | REL ACAS PRC | RERP | Smoke Detector Sensor Soiled | WOW03A03MDY | Control and protection System | 2640
2024-08-03 | 2025-05-05 | 2025-05-11 | 80400349 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Slip ring damaged | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2024-08-03 | 2025-06-16 | 2025-06-22 | 80400350 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Metal frame filter missing LSI | WOW03D03MU | Systems for conversion of energy | 27.34
2024-08-03 | 2025-03-24 | 2025-03-30 | 80400367 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Davit cowling detached from Davit and | WOW03A03XMM80GM001 | DAVIT Crane | 3815.38
2024-08-01 | 2025-05-05 | 2025-05-11 | 80400152 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Damaged Nacelle Crane Pendant Cable | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 5688.98
2024-08-01 | 2025-05-26 | 2025-06-01 | 80400153 | YR02 | Within a year | REL ACAS MACM PRC | RERP | TP gate missing lock | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 5440.65
2024-07-29 | 2025-04-21 | 2025-04-27 | 80399431 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | (Service) Smoke tests not carried out | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 420.04
2024-07-29 | 2024-08-27 | 2024-10-26 | 80399531 | YR02 | Within 3 months | CRTD ACAS MACM PRC | PLIP | Coolant leak on top of generator | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 460.54
2024-07-29 | 2025-06-09 | 2025-06-15 | 80399546 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Tower dehumidifier no coms | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 13713.72
2024-07-28 | 2025-06-23 | 2025-06-29 | 80399300 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Troubleshoot/replace tower dehumidifier | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1320
2024-07-28 | 2024-08-02 | 2024-08-25 | 80399375 | YR02 | Within 1 month | CRTD ACAS MACM PRC | COMP | CMM(2779), V164 De-Rate Code 36 Insp. Re | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 138680.23
2024-07-28 | 2025-07-07 | 2025-07-13 | 80399377 | YR02 | Immediately | REL ACAS MACM PRC | RERP | 3 spinner brackets cracked | WOW03H05MDA10 | Rotor & Hub Structure | 8621.58
2024-07-27 | 2025-06-23 | 2025-06-29 | 80399281 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wow03D05 Needle valve Dist block | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 518.91
2024-07-27 | 2025-06-23 | 2025-06-29 | 80399282 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wow03 D05 needle vv blade A | WOW03D05MDA11MQ001 | Blade A | 518.91
2024-07-25 | 2025-06-09 | 2025-06-15 | 80398993 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Avanti Lift Daily Logbook Full | WOW03A02XNM70 | Service Lift System | 0
2024-07-25 | 2025-06-09 | 2025-06-15 | 80398994 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Basement Hook On Points Not Certified | WOW03A02XSJ70FQ100 | Personal protection Tower bottom | 0
2024-07-25 | 2025-06-09 | 2025-06-15 | 80398995 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Prvs not tested | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 0
2024-07-25 | 2025-02-25 | 2025-03-03 | 80399008 | YR02 | Within a week | REL ACAS MACM PRC | RERP | PCM level 3 heater defective | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 1832.66
2024-07-25 | 2025-07-28 | 2025-08-03 | 80399124 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Pitch ram Slew bolts check/install | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 660
2024-07-25 | 2025-06-09 | 2025-06-15 | 80399127 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | PRV'S require testing | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 0
2024-07-23 | 2025-06-09 | 2025-06-15 | 80398676 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Faulty lift top/bottom limit switches | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 1320
2024-07-23 | 2025-04-14 | 2025-04-20 | 80398735 | YR02 | Within a week | REL PCNF ACAS CSER MACM PRC | RERP | Yaw motor error | WOW03H01MDL | Yaw system | 43406.25
2024-07-23 | 2025-08-18 | 2025-08-24 | 80398736 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP EXSC | Large oil spill in nacelle | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 1980
2024-07-23 | 2025-05-12 | 2025-05-18 | 80398744 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Hub centre plate assembly bolt snapped | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 0
2024-07-23 | 2025-06-23 | 2025-06-29 | 80398807 | YR02 | Within a year | CRTD ACAS CSER MACM PRC RELR | CRTD | *STATS* Davit crane | WOW03D05XMM80GM001-UM001 | Crane Unit (Main Boom & Pedestall) | 4330.08
2024-07-23 | 2025-06-09 | 2025-06-15 | 80398808 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | HMF nacelle crane boom fault 204! | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 0
2024-07-17 | 2025-05-12 | 2025-05-18 | 80398020 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 72474.12
2024-07-17 | 2025-08-18 | 2025-08-24 | 80398044 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Back up battery fault | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 36499.28
2024-07-17 | 2025-06-02 | 2025-06-08 | 80398062 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | REPL | Pitch tube Assembly replacement | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 81621.87
2024-07-16 | 2025-06-16 | 2025-06-22 | 80397863 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | AFA80 34KV switchgear SF6 Low Gas Alarm | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 0
2024-07-16 | 2025-02-25 | 2025-03-03 | 80397867 | YR02 | Within a week | REL ACAS GMPS MACM PRC | RERP | Major oil leakage found. (Pitch pipe ?) | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 71437.01
2024-07-16 | 2025-04-21 | 2025-04-27 | 80397869 | YR02 | Immediately | REL ACAS CSER MACM PRC | RERP | Hub main shaft broken. | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 1697.29
2024-07-16 | 2024-08-12 | 2025-07-08 | 80397904 | YR02 | Within a year | CRTD ACAS NMAT PRC | PLIP | Avanti Lift Missing DOC’s And Logbook | WOW03D01XNM70 | Service Lift System | 850
2024-07-16 | 2025-06-09 | 2025-06-15 | 80397905 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Tower First Aid Kit Expired. | WOW03A02XS | Safety service | 622.6
2024-07-16 | 2025-04-14 | 2025-04-20 | 80397928 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | *STATS* Davit crane | WOW03A02XMM80GM001-UM001 | Crane Unit (Main Boom & Pedestall) | 108.5
2024-07-15 | 2025-07-28 | 2025-08-03 | 80397771 | YR02 | Within 3 months | REL ACAS PRC | RERP EXSC PPMA | Brake hydraulic leakage high | WOW03H03MDX | Hydraulic system | 5280
2024-07-15 | 2025-06-23 | 2025-06-29 | 80397787 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | Motor not functioning correctly | WOW03D04MDX01GP001-MA001 | Motor | 313.88
2024-07-15 | 2024-08-14 | 2025-07-10 | 80397821 | YR02 | Within a year | CRTD ACAS NMAT PRC | PLIP | Hand rail on TP missing fixing bolts | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1700
2024-07-13 | 2025-06-16 | 2025-06-22 | 80397545 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wow03 D01 SPinner to hub hatch missing | WOW03D01UMD71 | Tower, doors and hatches | 5527.86
2024-07-12 | 2025-04-21 | 2025-04-27 | 80397029 | YR02 | Within 3 months | REL ACAS CSER GMPS MACM PRC | RERP | SLIP RING SPACER UPGRADE | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 1.76
2024-07-12 | 2025-02-28 | 2025-02-28 | 80397030 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-04-28 | 2025-05-04 | 80397033 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-28 | 2025-05-04 | 80397034 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-05-12 | 2025-05-18 | 80397035 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-21 | 2025-04-27 | 80397036 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-14 | 2025-04-20 | 80397037 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-05-26 | 2025-06-01 | 80397182 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2024-10-30 | 2024-10-30 | 80397184 | YR02 | Within 3 months | REL ACAS NMAT PRC | REXE EXSC | SLIP RING SPACER UPGRADE | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 1700
2024-07-12 | 2025-05-26 | 2025-06-01 | 80397185 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-07 | 2025-04-13 | 80397186 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-06-16 | 2025-06-22 | 80397188 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-06-23 | 2025-06-29 | 80397190 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-05-05 | 2025-05-11 | 80397193 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-03-01 | 2025-03-01 | 80397194 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-08-18 | 2025-08-24 | 80397195 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-06-09 | 2025-06-15 | 80397196 | YR02 | Within 3 months | REL ACAS GMPS MACM PRC | RERP | SLIP RING SPACER UPGRADE | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 1321.76
2024-07-12 | 2025-08-18 | 2025-08-24 | 80397197 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-05-05 | 2025-05-11 | 80397198 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-21 | 2025-04-27 | 80397199 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-04-07 | 2025-04-13 | 80397200 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-06-09 | 2025-06-15 | 80397201 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-06-02 | 2025-06-08 | 80397202 | YR02 | Within 3 months | REL PCNF ACAS CSER NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-08-04 | 2025-08-10 | 80397203 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 0
2024-07-12 | 2025-02-26 | 2025-02-26 | 80397204 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | SLIP RING SPACER UPGRADE | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 1320
2024-07-12 | 2025-05-26 | 2025-06-01 | 80397205 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | SLIP RING SPACER UPGRADE | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 1.76
2024-07-12 | 2025-04-07 | 2025-04-13 | 80397207 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | SLIP RING SPACER UPGRADE | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 0
2024-07-11 | 2025-05-12 | 2025-05-18 | 80396816 | YR02 | Immediately | REL ACAS CSER PRC | RERP | Loose hub hatch | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 0
2024-07-11 | 2025-04-07 | 2025-04-13 | 80396818 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Termination box cover stuck | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 0
2024-07-11 | 2025-07-14 | 2025-07-20 | 80396989 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | STATS: Seasight Davit Door | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 17948.98
2024-07-10 | 2025-03-31 | 2025-04-06 | 80396709 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Spinner bolts missing | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 6.54
2024-07-09 | 2025-06-09 | 2025-06-15 | 80396568 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | STATS: Seasight Davit Cowling | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 4475.38
2024-07-09 | 2025-07-07 | 2025-07-13 | 80396577 | YR02 | Immediately | CRTD ACAS CSER NMAT PRC | CRTD | STATS: First Aid Kit Expired | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2024-07-09 | 2025-04-07 | 2025-04-13 | 80396612 | YR02 | Within a week | REL PCNF ACAS MACM PRC | RERP | TCM(a), M-System | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 150950.71
2024-07-09 | 2025-07-07 | 2025-07-13 | 80396616 | YR02 | Immediately | REL ACAS CSER NMAT PRC | REPL | Nacelle first aid kit expired 05-2023 | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2024-07-09 | 2025-05-05 | 2025-05-11 | 80396652 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | STATS: Seasight Davit Cowling Removed | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 3589.53
2024-07-09 | 2025-05-12 | 2025-05-18 | 80396653 | YR02 | Within a year | REL ACAS CSER MACM PRC | REPL | STATS: Seasight Davit Cowling Removed | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 3589.53
2024-07-09 | 2025-03-24 | 2025-03-30 | 80396667 | YR02 | Within 3 months | REL PCNF ACAS CSER NMAT PRC | RERP | Rotor lock station leaking | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 0
2024-07-09 | 2025-04-21 | 2025-04-27 | 80396722 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Roof hydraulic rams leaking | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 0
2024-07-08 | 2025-03-24 | 2025-03-30 | 80396421 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | STATS: Seasight Davit Cowling Removed | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 3589.53
2024-07-08 | 2025-03-31 | 2025-04-06 | 80396422 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | STATS: TP And Nacelle First Aid Kits | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 1245.82
2024-07-07 | 2025-06-23 | 2025-06-29 | 80396281 | YR02 | Immediately | REL PCNF ACAS CSER NMAT PRC | RERP EXSC | Brake hydraulic leakage | WOW03C02MDX | Hydraulic system | 0
2024-07-05 | 2025-03-31 | 2025-04-06 | 80396058 | YR02 | Within a week | REL PCNF ACAS CSER GMPS MACM PRC | RERP MPTR | Stanchion brackets cracked | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 34697.94
2024-07-03 | 2025-06-23 | 2025-06-29 | 80395387 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | 2 spinner brackets cracked | WOW03D05MDA12 | Rotor blade arrangement B | 4551.72
2024-07-03 | 2025-05-05 | 2025-05-11 | 80395511 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Oil leak under generator | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 0
2024-07-03 | 2025-06-23 | 2025-06-29 | 80395513 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Battery string one has a leaking battery | WOW03D05BPE | Low voltage DC electrical main supply sy | 12152.41
2024-06-27 | 2025-06-02 | 2025-06-08 | 80394170 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Wieland plug checks | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2024-06-27 | 2025-02-28 | 2025-02-28 | 80394179 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Wieland plug checks | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 660
2024-06-27 | 2025-06-23 | 2025-06-29 | 80394224 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Investigate slow nacelle crane | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 5280
2024-06-26 | 2025-04-07 | 2025-04-13 | 80394007 | YR02 | Immediately | REL ACAS CSER MACM PRC | RERP | PitchBlockPilotPressLow 188bar | WOW03H04MDX | Hydraulic system | 354.5
2024-06-25 | 2025-06-16 | 2025-06-22 | 80393870 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Possible faulty RCB ( UMD75EX079-FC012 ) | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 77.41
2024-06-24 | 2025-05-19 | 2025-05-25 | 80393690 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | *STATS* Main Tower Ladder | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 1980
2024-06-24 | 2025-05-19 | 2025-05-25 | 80393691 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | *STATS* First aid kits | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 660
2024-06-24 | 2025-04-21 | 2025-04-27 | 80393692 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | *STATS* Davit crane | WOW03C06XMM80UH001 | Control Box Installation - Handheld | 0
2024-06-24 | 2025-06-09 | 2025-06-15 | 80393693 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Avanti Lift Daily Logbook | WOW03C06XN | Elevator System | 0
2024-06-24 | 2025-06-23 | 2025-06-29 | 80393694 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | *STATS* Main tower ladder | WOW03C06UMD73 | Tower, stairs and ladders (personal tran | 660
2024-06-24 | 2025-05-05 | 2025-05-11 | 80393780 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Main Internal Ladder Not Secured | WOW03C03UMD73 | Tower, stairs and ladders (personal tran | 877.6
2024-06-24 | 2025-05-12 | 2025-05-18 | 80393881 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | *STATS* First Aid Kit | WOW03E02XSP80 | Personal Safety Equipment, TP | 0
2024-06-24 | 2025-05-12 | 2025-05-18 | 80393882 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Main Internal Ladder Not Secured | WOW03E02UMD73 | Tower, stairs and ladders (personal tran | 0
2024-06-22 | 2025-04-14 | 2025-04-20 | 80393605 | YR02 | Within a week | REL ACAS CSER MACM PRC | RERP | hyd oil leak investigation | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 895.4
2024-06-21 | 2025-02-25 | 2025-03-03 | 80393512 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | REPL | Apparent interlocking issue | WOW03Z03AAF24WA001-QB001 | 34kV Switch gear disconnector | 0
2024-06-16 | 2025-03-10 | 2025-03-16 | 80391133 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Investigate HPU leak | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-06-16 | 2025-05-19 | 2025-05-25 | 80391134 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Remove hub acces hatch between blade A&C | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 12270.25
2024-06-14 | 2025-07-28 | 2025-08-03 | 80390899 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Hub lights not working | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 1953.75
2024-06-14 | 2025-05-19 | 2025-05-25 | 80390901 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | TCM(b), GbxA1Pln2-R | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 42026.23
2024-06-14 | 2025-05-19 | 2025-05-25 | 80390902 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | TCM(b), GbxA1Pln3-R | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-06-14 | 2025-05-19 | 2025-05-25 | 80390903 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | TCM(b), GbxA1Pln1-R | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-06-13 | 2025-05-26 | 2025-06-01 | 80390766 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Wow03 C04 LSI filter fan replacement | WOW03C04AAF | High voltage distribution >30kV-60 kV | 2694.52
2024-06-12 | 2025-05-26 | 2025-06-01 | 80390471 | YR02 | Within a week | REL ACAS CSER GMPS MACM PRC | RERP | Switchgear control remote/local isolater | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 147.91
2024-06-11 | 2025-03-24 | 2025-03-30 | 80390227 | YR02 | Immediately | REL ACAS NMAT PRC | RERP | First aid kits ood | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 660
2024-06-11 | 2025-05-05 | 2025-05-11 | 80390252 | YR02 | Within a week | REL ACAS CSER MACM PRC | RERP | Cac unit leaking into lower pcm levels | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 154.92
2024-06-11 | 2025-09-22 | 2025-09-28 | 80390446 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | STATS: Seasight Cowling Removed | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 4475.38
2024-06-11 | 2025-05-26 | 2025-06-01 | 80390461 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Nacelle crane slew very slow | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 0
2024-06-06 | 2025-02-25 | 2025-03-03 | 80389763 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Fit temporary nav light | WOW03Z03 | Off-shore substation Z03 | 0
2024-06-04 | 2025-05-05 | 2025-05-11 | 80388739 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | IPS batteries | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 14792.41
2024-06-04 | 2025-05-05 | 2025-05-11 | 80388740 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | Roof locking mechanism | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 143.88
2024-06-04 | 2024-07-02 | 2024-08-31 | 80389055 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | PLIP | damaged cable to offline filter | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 850
2024-06-04 | 2025-04-28 | 2025-05-04 | 80389056 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Hub plate centre assembly bolt snapped | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 219.68
2024-06-04 | 2025-04-21 | 2025-04-27 | 80389190 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | 3 cracked hub spinner support brackets | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 11557.47
2024-06-04 | 2025-05-05 | 2025-05-11 | 80389191 | YR02 | Within a week | REL PCNF ACAS MACM PRC | RERP | Bolts missing on main shaft bracket | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 1332.02
2024-06-04 | 2025-05-05 | 2025-05-11 | 80389203 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | LCTU CABLE | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 1467.27
2024-06-02 | 2025-04-14 | 2025-04-20 | 80388832 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | Main shaft pipes | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 44.48
2024-06-02 | 2025-08-18 | 2025-08-24 | 80388833 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | M16 Blank with Locking nut | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 1320
2024-06-01 | 2025-04-14 | 2025-04-20 | 80388675 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | Roof hatch handles broken | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 6445.28
2024-06-01 | 2025-04-28 | 2025-05-04 | 80388676 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Spinner support brackets | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 2461.2
2024-06-01 | 2025-04-28 | 2025-05-04 | 80388678 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Hub hatches locking mechanism | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 6990.25
2024-06-01 | 2025-04-28 | 2025-05-04 | 80388801 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Hub cabinet fixings | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 660
2024-05-29 | 2025-07-07 | 2025-07-13 | 80388370 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(b), GbxA1Pln2-T | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 44191.54
2024-05-29 | 2025-04-28 | 2025-05-04 | 80388402 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | Slip ring mounting bushes need replacing | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 7991.88
2024-05-28 | 2025-04-21 | 2025-04-27 | 80388040 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Silica bag from SwG missing | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2024-05-28 | 2025-04-14 | 2025-04-20 | 80388218 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Left spinner entry hatch seal missing | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 0
2024-05-27 | 2025-05-19 | 2025-05-25 | 80388015 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Seasight Davit Cowling Removed C01 | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 4475.38
2024-05-27 | 2025-05-26 | 2025-06-01 | 80388030 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Seasight Davit Cowling Removed | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 3815.38
2024-05-27 | 2025-04-21 | 2025-04-27 | 80388043 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Bad eyes in lower basement not inspected | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 0
2024-05-27 | 2025-04-21 | 2025-04-27 | 80388045 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Restriction to basement airtight | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 0
2024-05-27 | 2025-04-21 | 2025-04-27 | 80388046 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Missing Avanti Logbook | WOW03F03XNM70 | Service Lift System | 0
2024-05-26 | 2025-05-19 | 2025-05-25 | 80387899 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Nacelle First Aid Kit | WOW03C01XSP60 | Personal Safety Equipment, Nacelle/YAW | 0
2024-05-26 | 2025-05-19 | 2025-05-25 | 80387900 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | HMF Crane. | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2024-05-26 | 2025-04-14 | 2025-04-20 | 80387913 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | Gbox breather filter seal perished | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 5230.77
2024-05-26 | 2025-03-02 | 2025-03-02 | 80387915 | YR02 | Within a year | REL ACAS MACM PRC | RERP | *STATS* Seasight Davit | WOW03D02XMM80GM001 | DAVIT Crane | 774.56
2024-05-26 | 2025-03-31 | 2025-04-06 | 80387916 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | *STATS* TP Airtight Level Anchor points | WOW03D02XSP80FQ001 | Hook-on and Fall Arrest | 0
2024-05-26 | 2025-06-24 | 2025-06-30 | 80387917 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | *STATS* TP Airtight anchor Points | WOW03H01XSP80FQ001 | Hook-on and Fall Arrest | 0
2024-05-26 | 2025-05-19 | 2025-05-25 | 80387971 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Avanti Missing Certificate | WOW03C01XN | Elevator System | 0
2024-05-15 | 2025-04-07 | 2025-04-13 | 80386309 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | MDY50UC017 =BPE11FC001-FC002 breaker | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 3458.21
2024-05-14 | 2025-04-07 | 2025-04-13 | 80386217 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Seasight Davit Slew O-ring | WOW03H04XMM80GM001 | DAVIT Crane | 114.56
2024-05-14 | 2025-04-07 | 2025-04-13 | 80386219 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Seasight Davit Pedestal Cowling | WOW03H04XMM80GM001 | DAVIT Crane | 3815.38
2024-05-05 | 2025-06-09 | 2025-06-15 | 80385123 | YR02 | Within a week | REL ACAS MACM PRC | RERP | RM101 Damage | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 1570
2024-04-29 | 2025-04-07 | 2025-04-13 | 80384122 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Grid resonance filter temp Sw | WOW03B04MSE | Inverter system | 5628.17
2024-04-27 | 2025-05-19 | 2025-05-25 | 80383934 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Spinner access hatches damaged | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 10214.28
2024-04-27 | 2025-08-18 | 2025-08-24 | 80384011 | YR02 | Within 3 months | REL ACAS MACM PRC | REPL EXSC | Spinner bracket bolt missing | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 2016.02
2024-04-25 | 2025-05-12 | 2025-05-18 | 80383664 | YR02 | Within 1 month | REL PCNF ACAS CSER GMPS MACM PRC | RERP | Spinner support stanchions bolts sheared | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 96.6
2024-04-25 | 2025-05-05 | 2025-05-11 | 80383788 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Main shaft bracket damaged | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 0
2024-04-25 | 2025-05-05 | 2025-05-11 | 80383789 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Hub hatches not fitted | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 0
2024-04-25 | 2025-05-05 | 2025-05-11 | 80383805 | YR02 | Within a week | REL ACAS MACM PRC | RERP | Spinner entry hatch cracks | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 2353.28
2024-04-22 | 2025-09-22 | 2025-09-28 | 80383348 | YR02 | Within a week | REL PCNF ACAS NMAT PRC | RERP | Check spinner support stanchions | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 5280
2024-04-22 | 2025-09-22 | 2025-09-28 | 80383363 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Leak on HPU | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 5280
2024-04-22 | 2025-09-22 | 2025-09-28 | 80383364 | YR02 | Within a week | REL ACAS MACM PRC | RERP | Contactor MDX01GP001-QA001 replacement | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 1361.7
2024-04-17 | 2025-06-23 | 2025-06-29 | 80382606 | YR02 | Within a week | REL ACAS CSER NMAT PRC | RERP | Backup generator leaking oil | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 0
2024-04-17 | 2025-07-28 | 2025-08-03 | 80382612 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP EXSC MATR | CMM(2673), V164 Twr Open Breather Leak I | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 8255.35
2024-04-17 | 2025-04-21 | 2025-04-27 | 80382613 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 17121.33
2024-04-17 | 2025-03-24 | 2025-03-30 | 80382614 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP | Wind sensor alignment | WOW03A03 | Wind Turbine A03_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-03-31 | 2025-04-06 | 80382615 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 23344.11
2024-04-17 | 2025-04-21 | 2025-04-27 | 80382616 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 23072.73
2024-04-17 | 2025-04-28 | 2025-05-04 | 80382617 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-04-14 | 2025-04-20 | 80382618 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-06-09 | 2025-06-15 | 80382619 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wind sensor alignment | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-05-05 | 2025-05-11 | 80382620 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 23072.73
2024-04-17 | 2025-05-26 | 2025-06-01 | 80382781 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-06-09 | 2025-06-15 | 80382782 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wind sensor alignment | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 15230.74
2024-04-17 | 2025-05-26 | 2025-06-01 | 80382783 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-08-11 | 2025-08-17 | 80382784 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-06-30 | 2025-07-06 | 80382785 | YR02 | Within 3 months | REL PCNF ACAS CSER GMPS MACM PRC | RERP | Wind sensor alignment | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 21388.85
2024-04-17 | 2025-06-23 | 2025-06-29 | 80382788 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 20510.73
2024-04-17 | 2025-04-14 | 2025-04-20 | 80382789 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-07-07 | 2025-07-13 | 80382790 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-07-07 | 2025-07-13 | 80382791 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-08-18 | 2025-08-24 | 80382792 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-04-21 | 2025-04-27 | 80382793 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wind sensor alignment | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-09-01 | 2025-09-07 | 80382794 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wind sensor alignment | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-05-05 | 2025-05-11 | 80382796 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 20510.73
2024-04-17 | 2025-04-21 | 2025-04-27 | 80382797 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-06-09 | 2025-06-15 | 80382798 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-07-28 | 2025-08-03 | 80382799 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 23344.11
2024-04-17 | 2025-06-02 | 2025-06-08 | 80382800 | YR02 | Within 3 months | REL PCNF ACAS MACM PRC | RERP | Wind sensor alignment | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 22440.69
2024-04-17 | 2025-08-25 | 2025-08-31 | 80382801 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Wind sensor alignment | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-04-14 | 2025-04-20 | 80382802 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 17118.25
2024-04-17 | 2025-05-26 | 2025-06-01 | 80382803 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Wind sensor alignment | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 15230.73
2024-04-17 | 2025-07-28 | 2025-08-03 | 80382804 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 23311.29
2024-04-17 | 2025-04-07 | 2025-04-13 | 80382805 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 14533.27
2024-04-13 | 2025-09-08 | 2025-09-14 | 80382279 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Generator drain hose damaged | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 1980
2024-04-11 | 2025-05-05 | 2025-05-11 | 80382128 | YR02 | Immediately | REL PCNF ACAS MACM PRC | RERP | EMF Acc 2 Press Low, 209.0 bar | WOW03C03MDX | Hydraulic system | 19694.31
2024-04-09 | 2025-06-23 | 2025-06-29 | 80380681 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Main shaft cable bracket | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 3088.69
2024-04-08 | 2025-03-04 | 2025-03-10 | 80380480 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Post MCE 3 month inspection | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 39788.46
2024-04-08 | 2025-05-12 | 2025-05-18 | 80380527 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Investigate water ingress issue - 316856 | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 660
2024-04-07 | 2025-06-23 | 2025-06-29 | 80380439 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Hub Hatch Damage | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 5477.47
2024-04-07 | 2025-06-23 | 2025-06-29 | 80380440 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Nacelle coolant system | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 10716.74
2024-04-07 | 2025-06-16 | 2025-06-22 | 80380462 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Wow03 e04 Roof bracket removal | WOW03E04ZY | Struct. f. communication and information | 0
2024-04-04 | 2025-06-16 | 2025-06-22 | 80380185 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | Brake temp sensor | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 222.64
2024-04-02 | 2025-06-23 | 2025-06-29 | 80379627 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | AAF80 switchgear requires an Ops Lock | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 1980
2024-04-02 | 2025-04-21 | 2025-04-27 | 80379672 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | Missing Hub Access Hatch | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 6952.09
2024-04-02 | 2025-06-23 | 2025-06-29 | 80379674 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | V seal leaking | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 1980
2024-04-02 | 2025-08-18 | 2025-08-24 | 80379675 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | TCM(b), GbxA1Pln3-R | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 44374.54
2024-03-29 | 2025-05-12 | 2025-05-18 | 80379113 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | Cleaning of oil leak on nacelle/ turbine | WOW03E04 | Wind Turbine E04_MHIV V164 MK1A 8.0 | 0
2024-03-28 | 2025-04-14 | 2025-04-20 | 80379055 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Tower CAC unit floor seal | WOW03G02 | Wind Turbine G02_MHIV V164 MK1A 8.0 | 155.7
2024-03-21 | 2025-06-30 | 2025-07-06 | 80377876 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | D03 external fuel tank empty | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 0
2024-03-18 | 2025-06-30 | 2025-07-06 | 80377011 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Hub Accumulator bracket left in helideck | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 0
2024-03-18 | 2025-03-17 | 2025-03-23 | 80377180 | YR02 | Within a week | CRTD ACAS CSER NMAT PRC | CRTD | Crack found on accumulator racking. | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 0
2024-03-12 | 2025-12-29 | 2026-01-04 | 80376466 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Nacelle 230V Socket replacement | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 0
2024-03-12 | 2025-08-18 | 2025-08-24 | 80376556 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP | Hub Light Socket Damaged | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 1518.44
2024-03-12 | 2025-10-27 | 2025-11-02 | 80376566 | YR02 | Within 3 months | CRTD ACAS CSER MACM PRC | CRTD | Basement ladder is damaged | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 105.75
2024-03-12 | 2025-09-08 | 2025-09-14 | 80376581 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Lift floor plate needs repairing/inspect | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 0
2024-03-11 | 2025-06-23 | 2025-06-29 | 80376340 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Fog signal checks | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 1980
2024-03-11 | 2025-04-28 | 2025-05-04 | 80376347 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Fog signal checks | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 1980
2024-03-11 | 2025-08-11 | 2025-08-17 | 80376349 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Fog signal checks | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 1980
2024-03-11 | 2025-06-30 | 2025-07-06 | 80376350 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Fog signal checks | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 1980
2024-03-11 | 2025-06-30 | 2025-07-06 | 80376352 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Fog signal checks | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 1980
2024-03-11 | 2025-09-08 | 2025-09-14 | 80376353 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Fog signal checks | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 0
2024-03-05 | 2025-04-14 | 2025-04-20 | 80375431 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Replace coupling house hatch | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 1980
2024-03-01 | 2025-07-21 | 2025-07-27 | 80374969 | YR02 | Within a year | REL PCNF ACAS NMAT PRC | RERP | Hub Hatch Checks | WOW03E02MDA | Rotor structure, Hub and Blades | 1980
2024-03-01 | 2025-09-01 | 2025-09-07 | 80374973 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Hub Hatch Checks | WOW03F02MDA | Rotor structure, Hub and Blades | 1980
2024-03-01 | 2025-09-08 | 2025-09-14 | 80374977 | YR02 | Within a year | REL PCNF ACAS CSER NMAT PRC | RERP | Hub Hatch Checks | WOW03G04MDA | Rotor structure, Hub and Blades | 0
2024-02-27 | 2025-04-14 | 2025-04-20 | 80373944 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | CMM(2671), V164 Twr Open Breather Level | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 2663.18
2024-02-26 | 2025-10-27 | 2025-11-02 | 80373827 | YR02 | Within a year | REL PCNF ACAS NMAT PRC | RERP | Hub cabinet support bracket inspection | WOW03D05MDA10UL001 | Rotor Hub Installation | 1320
2024-02-21 | 2025-04-07 | 2025-04-13 | 80372951 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | AtoN Navigation light checks | WOW03D01XSD81 | Navigation marine aids signalling - TP | 0
2024-02-21 | 2025-06-30 | 2025-07-06 | 80372953 | YR02 | Within 1 month | REL PCNF ACAS NMAT PRC | RERP | AtoN Navigation light checks | WOW03H01XSD81 | Navigation marine aids signalling - TP | 990
2024-02-21 | 2025-09-08 | 2025-09-14 | 80372954 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | AtoN Navigation light checks | WOW03H04XSD81 | Navigation marine aids signalling - TP | 0
2024-02-21 | 2025-05-26 | 2025-06-01 | 80373008 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Digital disply defective on UPS | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 31592.43
2024-02-20 | 2025-03-03 | 2025-03-03 | 80372597 | YR02 | Immediately | REL ACAS MACM PRC | RERP | AC unit fan error and leak | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 2811.58
2024-02-15 | 2025-04-07 | 2025-04-13 | 80370943 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Aviation equipment error | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 0
2024-02-15 | 2025-06-09 | 2025-06-15 | 80371968 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Power backup battery string error | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 0
2024-02-14 | 2025-06-16 | 2025-06-22 | 80370882 | YR02 | Within 3 months | REL PCNF ACAS GMPS MACM PRC | RERP EXSC MATR | CMM(2672), V164 Nac Open Breather Leak I | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 8701.65
2024-02-13 | 2025-06-09 | 2025-06-15 | 80370542 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | HVCB Troubleshooting Required | WOW03C02AFA70QA001 | Switchgear 36kV - Circuit breaker panel | 0
2024-02-13 | 2025-09-22 | 2025-09-28 | 80370622 | YR02 | Within 1 month | REL PCNF ACAS CSER GMPS MACM PRC | RERP | Hydralic pump 1 not running | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 48688.45
2024-02-13 | 2025-09-22 | 2025-09-28 | 80370624 | YR02 | Within a week | REL ACAS NMAT PRC | RERP | Excessive oil leak under generator | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 5280
2024-02-10 | 2025-04-14 | 2025-04-20 | 80369896 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Salt Water on Transformer LV Connections | WOW03E01MST70TA001-TA001 | Transformer | 5280
2024-02-10 | 2025-09-22 | 2025-09-28 | 80369928 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Smoke Detector Sensor | WOW03D04CKA | Fire alarm system | 15600.4
2024-02-10 | 2025-04-14 | 2025-04-20 | 80370082 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | LSI Coolant pipe work leaing | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 11883.42
2024-02-09 | 2025-10-27 | 2025-11-02 | 80369879 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Sump on Back up generator needs cleaning | WOW03D05BRA01FC075 | Generator backup | 5280
2024-02-07 | 2025-05-26 | 2025-06-01 | 80369460 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | Tower Dehumidifier alarm | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 807.85
2024-02-07 | 2025-04-21 | 2025-04-27 | 80369485 | YR02 | Within 1 month | REL ACAS CSER GMPS MACM PRC | RERP | CMM(2920), Wind Sensor Misalign.Insp. Re | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 23088.58
2024-02-03 | 2025-06-23 | 2025-06-29 | 80368774 | YR02 | Within a week | REL ACAS CSER NMAT PRC | RERP | D04 small gate hatc lock broke and gate | WOW03D04UMD80UM001 | Transition Piece Section | 0
2024-02-03 | 2025-04-07 | 2025-04-13 | 80368972 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL | Damage to fibreglass on spinner wow3 b04 | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 10560
2024-01-30 | 2025-10-27 | 2025-11-02 | 80368556 | YR02 | Within 1 month | REL PCNF ACAS CSER PRC | RERP | Hub cabinet to centre plate bolts missin | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 0
2024-01-30 | 2025-04-21 | 2025-04-27 | 80368662 | YR02 | Within 3 months | REL PCNF ACAS CSER MACM PRC | RERP | Hub hatch for blade c damaged | WOW03F03 | Wind Turbine F03_MHIV V164 MK1A 8.0 | 3733.03
2024-01-13 | 2025-09-08 | 2025-09-14 | 80366783 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | AAF80 SWG SF6 Alarm Not Tested | WOW03G03AAF80WA001 | Switch gear installation | 660
2024-01-11 | 2025-06-09 | 2025-06-15 | 80366305 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | G02 Wow03 emc cable shroud LSI fire DET | WOW03G02XG | Fire extinguishing system | 660
2024-01-11 | 2025-08-18 | 2025-08-24 | 80366340 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Replace main tank air hose | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 33.39
2024-01-10 | 2025-09-22 | 2025-09-28 | 80366170 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | Aviation light configuration | WOW03H05CKD51PF001-PF001 | Signal lamp | 0
2024-01-06 | 2025-05-26 | 2025-06-01 | 80365733 | YR02 | Within 3 months | REL ACAS GMPS MACM PRC | RERP | Replace broken ladder brackets | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 2088.8
2024-01-06 | 2025-06-02 | 2025-06-08 | 80365748 | YR02 | Within 1 month | REL ACAS NMAT PRC | REPL EXSC | Water at front lower section of nacelle | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 1980
2024-01-05 | 2025-02-25 | 2025-03-03 | 80365680 | YR02 | Within a week | REL ACAS CSER NMAT PRC | REPL | BoP (Class 2) WOW03Z03CFU01 | WOW03Z03CFU01 | Station Control System (SCS) Generator | 0
2024-01-03 | 2025-05-26 | 2025-06-01 | 80365298 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | Damaged slip ring found | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 51718.52
2023-12-14 | 2025-04-28 | 2025-05-04 | 80362653 | YR02 | Within 1 month | REL ACAS CSER PRC | RERP | Lift guide to be replaced | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 0
2023-12-14 | 2025-05-05 | 2025-05-11 | 80362721 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Investigate defective PCM hoist | WOW03F02 | Wind Turbine F02_MHIV V164 MK1A 8.0 | 0
2023-12-14 | 2025-09-08 | 2025-09-14 | 80362722 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Investigate defective PCM hoist | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 5280
2023-12-12 | 2025-05-19 | 2025-05-25 | 80362485 | YR02 | Within a year | REL ACAS CSER PRC | RERP | Salt on top of lsi | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2023-12-11 | 2025-03-31 | 2025-04-06 | 80362406 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Aviation and heli lights | WOW03A04 | Wind Turbine A04_MHIV V164 MK1A 8.0 | 77612.06
2023-12-10 | 2025-06-30 | 2025-07-06 | 80362272 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Aviation Equipment Error | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 73652.06
2023-12-02 | 2025-05-05 | 2025-05-11 | 80361665 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Accumulator bracket replacements | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 223152.32
2023-12-02 | 2025-10-06 | 2025-10-12 | 80361686 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | Cabinet door on blade A | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2023-12-02 | 2025-07-07 | 2025-07-13 | 80361687 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Screws missing from msi ct414 | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2023-12-02 | 2025-06-16 | 2025-06-22 | 80361688 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | AFA70 CB OPS Counter missing spring | WOW03B02AFA70QA001 | Switchgear 36kV - Circuit breaker panel | 5280
2023-11-26 | 2025-10-27 | 2025-11-02 | 80361034 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | V seal | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 0
2023-11-18 | 2025-05-19 | 2025-05-25 | 80360445 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | V164 Gearbox Valve Actuator Adjustment | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 0
2023-11-17 | 2025-04-21 | 2025-04-27 | 80360056 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Spinner hatch lever missing | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2023-11-17 | 2025-09-01 | 2025-09-07 | 80360212 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | External nacelle bolts | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 1320
2023-11-17 | 2025-10-06 | 2025-10-12 | 80360305 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Hub RCCB | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 1929.96
2023-11-17 | 2025-10-06 | 2025-10-12 | 80360376 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Loose bolted connections in spinner | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 1320
2023-11-16 | 2025-06-23 | 2025-06-29 | 80360044 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Nacelle hyd pipe brackets missing | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 2346.66
2023-11-16 | 2025-04-28 | 2025-05-04 | 80360052 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Replace MSE72KF001-KF001 CT414LSI | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 8240.57
2023-11-16 | 2025-04-28 | 2025-05-04 | 80360109 | YR02 | Within a year | REL ACAS CSER PRC | RERP | CMM(2810), Hub Hyd System Pressure Insp. | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 0
2023-11-16 | 2025-04-28 | 2025-05-04 | 80360174 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Found signs of water on busbar in lsi | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 793.78
2023-11-15 | 2025-06-23 | 2025-06-29 | 80360042 | YR02 | Within a week | REL ACAS CSER NMAT PRC | RERP | Blade C cabinet door and bracket broken | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 0
2023-11-03 | 2025-04-28 | 2025-05-04 | 80358910 | YR02 | Within 1 month | REL ACAS PRC | RERP | 4757 Aviation Equipment Error | WOW03A05 | Wind Turbine A05_MHIV V164 MK1A 8.0 | 1980
2023-11-03 | 2025-10-27 | 2025-11-02 | 80358911 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP MATR | 4757 Aviation Equipment Error | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 73652.06
2023-11-03 | 2025-07-28 | 2025-08-03 | 80358982 | YR02 | Within 1 month | REL ACAS CSER PRC | RERP | Aviation Light Error | WOW03H03 | Wind Turbine H03_MHIV V164 MK1A 8.0 | 0
2023-11-03 | 2025-07-21 | 2025-07-27 | 80358983 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | 4757 Aviation Equipment Error | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 73595.47
2023-11-02 | 2025-06-23 | 2025-06-29 | 80358775 | YR02 | Within 3 months | REL ACAS PRC | RERP | Leak on pump 2 on HPU. | WOW03A01MDX01 | Hydraulic system | 1320
2023-11-01 | 2025-05-05 | 2025-05-11 | 80358803 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Internal crane damage | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 0
2023-10-31 | 2025-06-16 | 2025-06-22 | 80358636 | YR02 |  | CRTD ACAS CSER NMAT PRC | CRTD | 2021 AIM Missing Grating Clip | WOW03E04UMD80UM001-WS021 | Lower Work Platform | 0
2023-10-31 | 2025-06-09 | 2025-06-15 | 80358637 | YR02 |  | CRTD ACAS NMAT PRC | CRTD | 2021 AIM Confined Space Trip Hazard G01 | WOW03G01UMD80UM001-WS011 | Air Tight Platform | 0
2023-10-31 | 2025-10-06 | 2025-10-12 | 80358653 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Hub accumulator racking | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 0
2023-10-31 | 2025-09-08 | 2025-09-14 | 80358685 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Missing Roxtec Bung | WOW03H04UMD80UM001-WS011 | Air Tight Platform | 0
2023-10-30 | 2025-10-06 | 2025-10-12 | 80358564 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Roof levers leaking | WOW03F05X | ANCILLARY SYSTEMS | 7305.39
2023-10-28 | 2025-04-21 | 2025-04-27 | 80358375 | YR02 | Immediately | REL PCNF ACAS CSER GMPS MACM PRC | RERP MPTR | Hub controller 24V PSU DC failure 1 & 2 | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 4933.16
2023-10-25 | 2025-02-27 | 2025-02-27 | 80358212 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | WI-FI | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 5280
2023-10-23 | 2025-09-22 | 2025-09-28 | 80357591 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | Gear Oil Offline Pump Low Pressure | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 2640
2023-10-22 | 2025-05-05 | 2025-05-11 | 80357545 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(b), Oil debris sensors | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 153716.39
2023-10-18 | 2025-04-07 | 2025-04-13 | 80355778 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03B04 | Wind Turbine B04_MHIV V164 MK1A 8.0 | 79074.12
2023-10-18 | 2025-03-31 | 2025-04-06 | 80357224 | YR02 | Within a year | REL ACAS CSER PRC | RERP | CMM(2810), Hub Accumulator Capacity Insp | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 0
2023-10-18 | 2025-06-30 | 2025-07-06 | 80357263 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Rccb | WOW03D03MDY10UC001-FB001 | Residual current circuit breaker | 954.81
2023-10-17 | 2025-10-27 | 2025-11-02 | 80356062 | YR02 | Within a week | REL ACAS GMPS MACM PRC | RERP | TCM(a), M-System | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 152076.83
2023-10-07 | 2025-06-30 | 2025-07-06 | 80354895 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | TCM(b), M-System | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 149630.71
2023-10-07 | 2025-04-07 | 2025-04-13 | 80354964 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | GearboxA1PlanetRECarrierBearingTempHigh | WOW03G01 | Wind Turbine G01_MHIV V164 MK1A 8.0 | 1664.29
2023-10-03 | 2025-09-22 | 2025-09-28 | 80352012 | YR02 | Within a year | REL ACAS MACM PRC | RERP | Hydraulic pipe bracket missing | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 6862.08
2023-10-03 | 2025-07-07 | 2025-07-13 | 80352013 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Detached Equipotential Bonding | WOW03E03UMD80WS001 | External Platform | 0
2023-10-02 | 2025-03-17 | 2025-03-23 | 80351778 | YR02 | Within 1 month | CRTD ACAS MSPT PRC | CRTD | CMM(2900), V164 hyd oil temp | WOW03D01 | Wind Turbine D01_MHIV V164 MK1A 8.0 | 2267.86
2023-09-22 | 2025-04-14 | 2025-04-20 | 80351109 | YR02 | Immediately | REL PCNF ACAS CSER PRC | RERP | Blade B and C accumulator brack cracked | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 0
2023-09-22 | 2023-12-06 | 2023-12-12 | 80351111 | YR02 | Within 3 months | CRTD ACAS MACM PRC | COMP | CMM(2670), V164 Nac Open Breather Level | WOW03H05 | Wind Turbine H05_MHIV V164 MK1A 8.0 | 2503.98
2023-09-22 | 2025-04-07 | 2025-04-13 | 80351304 | YR02 | Immediately | REL ACAS MACM PRC | REPL | Blade A accumulator bracket crack | WOW03D03MD | Wind turbine system | 127416.16
2023-09-02 | 2025-06-09 | 2025-06-15 | 80349356 | YR02 | Within a year | REL ACAS MACM PRC | RERP | TP Gate latch crack | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 5440.65
2023-09-02 | 2025-05-19 | 2025-05-25 | 80349397 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | C01 Slow HMF Nacelle Crane | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 0
2023-09-02 | 2025-04-28 | 2025-05-04 | 80349398 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | TP Gate latch crack | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 0
2023-09-01 | 2025-09-22 | 2025-09-28 | 80349235 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | Floor plate bolt sheared | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 6600.96
2023-08-31 | 2025-05-05 | 2025-05-11 | 80349216 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Wow3 A04 Light in tower u/s | WOW03A04WBA02 | Emergency lighting system | 151.78
2023-08-31 | 2025-05-05 | 2025-05-11 | 80349253 | YR02 | Within a year | REL ACAS MACM PRC | RERP | C04 Coupling Panel Opening | WOW03C03 | Wind Turbine C03_MHIV V164 MK1A 8.0 | 9565.69
2023-08-27 | 2025-09-22 | 2025-09-28 | 80348714 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Wi-Fi not working in Nacelle | WOW03C05YC | IT Network | 1320
2023-08-26 | 2025-06-23 | 2025-06-29 | 80348672 | YR02 | Within a week | REL ACAS GMPS MACM PRC | RERP | TCM(a), M-System | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 152076.83
2023-08-19 | 2025-05-26 | 2025-06-01 | 80348142 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Damage on equipotential connection | WOW03C04UMD80WS001 | External Platform | 1320
2023-08-18 | 2025-05-26 | 2025-06-01 | 80347925 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Junction box I/o blade c hub damage | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2023-08-18 | 2025-06-16 | 2025-06-22 | 80347942 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | TCM(b), GbxA1Pln3-R | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 44908.66
2023-08-16 | 2025-04-21 | 2025-04-27 | 80347551 | YR02 | Within 3 months | REL ACAS CSER MSPT PRC | REMA | Replace generator cooling fans | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 117725.98
2023-08-16 | 2025-06-23 | 2025-06-29 | 80347600 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | TCM(a), M-System | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 1320
2023-08-14 | 2025-07-07 | 2025-07-13 | 80347302 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | Investigate LCTU Cable found on TP | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 1809.08
2023-08-10 | 2025-04-07 | 2025-04-13 | 80346498 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | Blade A ball valve locking pin | WOW03B04MDX11QN001 | Valve block | 6710.93
2023-08-04 | 2025-06-23 | 2025-06-29 | 80346027 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Damaged power cable plug to slip ring | WOW03D04 | Wind Turbine D04_MHIV V164 MK1A 8.0 | 36286.47
2023-08-03 | 2025-12-29 | 2026-01-04 | 80345860 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | WTG Tower switch | WOW03C02YCC01XH101-WE001 | Earthing Line FO Box | 20002.99
2023-07-30 | 2025-06-30 | 2025-07-06 | 80345694 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | H01 Roof Hydraulic Leak | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 3345.39
2023-07-30 | 2025-05-19 | 2025-05-25 | 80345709 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | TCM(b), M-System | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 152077.68
2023-07-28 | 2025-06-09 | 2025-06-15 | 80345495 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | M8 screw missing from LCTU sliding ring | WOW03C02 | Wind Turbine C02_MHIV V164 MK1A 8.0 | 0
2023-07-28 | 2025-06-02 | 2025-06-08 | 80345575 | YR02 | Within 3 months | REL ACAS NMAT PRC | RERP | INSTALL GUARDS TO COVER ABOVE ROTOR | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 660
2023-07-24 | 2025-04-14 | 2025-04-20 | 80345145 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | ACCUMILATOR BRACKET CHECKS | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 0
2023-07-12 | 2025-02-25 | 2025-03-03 | 80344097 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | REPL | SCADA - WTG UPS | WOW03Z03CAA01UH001-RB001 | UPS | 0
2023-07-11 | 2025-05-19 | 2025-05-25 | 80344111 | YR02 | Within a week | CRTD ACAS CSER MACM PRC | CRTD | E02 CAC leaking | WOW03E02 | Wind Turbine E02_MHIV V164 MK1A 8.0 | 623.99
2023-07-10 | 2025-04-28 | 2025-05-04 | 80344044 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | Rotor lock grease upgrade | WOW03B01MDA15 | Rotor lock system | 0
2023-07-09 | 2025-05-05 | 2025-05-11 | 80343929 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | F04 tower Dehumidifier ready for service | WOW03F04 | Wind Turbine F04_MHIV V164 MK1A 8.0 | 13713.72
2023-07-08 | 2025-12-29 | 2026-01-04 | 80343851 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | B05 no Wi-Fi in nacelle | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 0
2023-07-04 | 2025-06-30 | 2025-07-06 | 80343119 | YR02 | Within a year | REL ACAS CSER NMAT PRC | REPL | SWG cabinet doors broken | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 0
2023-07-04 | 2025-05-19 | 2025-05-25 | 80343244 | YR02 | Within 3 months | REL PCNF ACAS CSER NMAT PRC | RERP | Wow3 C02 pump no.3 on Hpu investigation | WOW03C02MDX01GP003 | Motor Pump 3 Assy 50 Hz (Pos 16) | 0
2023-06-29 | 2025-06-30 | 2025-07-06 | 80342777 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | PRVs missed on stats | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 0
2023-06-29 | 2025-04-14 | 2025-04-20 | 80342844 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Hydraulic Filter Indicator Seal Replace | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 3.57
2023-06-28 | 2025-09-22 | 2025-09-28 | 80342734 | YR02 | Within a year | CRTD ACAS MACM PRC | CRTD | Coating Damage at TP Flange Connection | WOW03H05UMD80UM001-WS001 | Upper Level Platform | 3128.99
2023-06-28 | 2025-08-18 | 2025-08-24 | 80342788 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | TCM(b), GbxA1Pln3-T | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 44374.54
2023-06-23 | 2025-10-06 | 2025-10-12 | 80342316 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | No Wi-Fi | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 660
2023-06-22 | 2025-04-21 | 2025-04-27 | 80342307 | YR02 | Within a week | REL ACAS MACM PRC | RERP | TCM(a), M-System | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 158017.68
2023-06-22 | 2025-06-23 | 2025-06-29 | 80342346 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | C04 hub dist block damage to QM003 QM004 | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 4279.74
2023-06-21 | 2025-06-23 | 2025-06-29 | 80342249 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | PRV distribution block and pump station | WOW03C06MDX01 | Hydraulic system | 0
2023-06-21 | 2025-05-26 | 2025-06-01 | 80342251 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | C04 no Wi-Fi in tower or nacelle | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 2640
2023-06-19 | 2025-08-18 | 2025-08-24 | 80341917 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | F01 gas struts not fitted to floor hatch | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 1320
2023-06-13 | 2025-04-21 | 2025-04-27 | 80341346 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | Rotor lock pins upgrade required | WOW03B03MDA15 | Rotor lock system | 715.92
2023-06-08 | 2025-02-03 | 2025-02-09 | 80340969 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | H01 HMF crane spare battery | WOW03H | WTG in row H (RDS-PP) | 930.55
2023-06-08 | 2025-06-30 | 2025-07-06 | 80340987 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | H01 Cabinet Heating Elements | WOW03H01 | Wind Turbine H01_MHIV V164 MK1A 8.0 | 3702.84
2023-06-08 | 2025-05-05 | 2025-05-11 | 80340998 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | New HMF batteries and umbilical needed. | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 30744.79
2023-06-04 | 2025-04-14 | 2025-04-20 | 80340638 | YR02 | Within 1 month | CRTD ACAS CSER NMAT PRC | CRTD | New Wi-Fi router required | WOW03A02YC | IT Network | 0
2023-05-29 | 2026-02-16 | 2026-02-22 | 80340365 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | C07 - Troubleshoot Aviation lights | WOW03C07 | Wind Turbine C07_MHIV V164 MK1A 8.0 | 0
2023-05-29 | 2025-08-18 | 2025-08-24 | 80340368 | YR02 | Within 1 month | REL PCNF ACAS PRC | RERP EXSC PPMA | F01 - Troubleshoot Aviation lights | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 7920
2023-05-18 | 2025-04-21 | 2025-04-27 | 80339133 | YR02 | Within 3 months | REL PCNF ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03B03 | Wind Turbine B03_MHIV V164 MK1A 8.0 | 17160.69
2023-05-18 | 2025-04-14 | 2025-04-20 | 80339134 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03A02 | Wind Turbine A02_MHIV V164 MK1A 8.0 | 24147.83
2023-05-18 | 2025-05-19 | 2025-05-25 | 80339136 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Wind sensor alignment | WOW03C01 | Wind Turbine C01_MHIV V164 MK1A 8.0 | 20510.73
2023-05-18 | 2025-12-29 | 2026-01-04 | 80339138 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Wind sensor alignment | WOW03B05 | Wind Turbine B05_MHIV V164 MK1A 8.0 | 0
2023-05-18 | 2025-05-26 | 2025-06-01 | 80339139 | YR02 | Within 3 months | REL ACAS CSER MACM PRC | RERP | Wind sensor alignment | WOW03B02 | Wind Turbine B02_MHIV V164 MK1A 8.0 | 14533.27
2023-05-11 | 2025-04-14 | 2025-04-20 | 80338531 | YR02 | Within 1 month | CRTD ACAS CSER MACM PRC | CRTD | Rotor lock upgrade | WOW03A02MDA15 | Rotor lock system | 987.44
2023-05-11 | 2025-09-08 | 2025-09-14 | 80338583 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | Repair gap in damper level floor | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 2640
2023-04-30 | 2025-06-23 | 2025-06-29 | 80337348 | YR02 | Within a year | CRTD ACAS CSER MACM PRC | CRTD | Rotor lock grease upgrade | WOW03D04MDA15 | Rotor lock system | 231.95
2023-04-27 | 2025-08-11 | 2025-08-17 | 80337151 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | Replace damaged M-System cables | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 2723.32
2023-04-25 | 2025-06-02 | 2025-06-08 | 80336932 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | Correct RDS code on cable | WOW03E03 | Wind Turbine E03_MHIV V164 MK1A 8.0 | 0
2023-04-09 | 2025-06-23 | 2025-06-29 | 80335303 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Nacelle hydraulic crane function | WOW03A01XMM | Crane, hoists for conversion of energy | 0
2023-04-06 | 2025-08-18 | 2025-08-24 | 80334860 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | F01 loose hatch lock handle in hub | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 8310.25
2023-04-05 | 2025-04-21 | 2025-04-27 | 80334899 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | F01 new CAC filters on pcm4 | WOW03F01 | Wind Turbine F01_MHIV V164 MK1A 8.0 | 0
2023-04-04 | 2025-02-25 | 2025-03-03 | 80334886 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | REPL | All BCUs - alarm status incorrect | WOW03Z03AAF | MEDIUM VOLTAGE DISTRIBUTION 34kV | 0
2023-04-04 | 2025-02-25 | 2025-03-03 | 80334887 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | REPL | AAF11 KF001 BCU not able to operate | WOW03Z03AAF | MEDIUM VOLTAGE DISTRIBUTION 34kV | 0
2023-03-31 | 2025-08-18 | 2025-08-24 | 80334401 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | C05 tetra batteries damaged | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 1320
2023-03-22 | 2025-02-25 | 2025-03-03 | 80333347 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | REPL | WOW03 Asset Library incorrect Circuit | WOW03Z03 | Off-shore substation Z03 | 0
2023-03-15 | 2025-10-06 | 2025-10-12 | 80332493 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Wi-Fi power cycle – Tower | WOW03F05UMD70 | Tower System | 660
2023-03-15 | 2025-07-28 | 2025-08-03 | 80332495 | YR02 | Within 3 months | CRTD ACAS NMAT PRC | CRTD | Wi-Fi power cycle – Tower | WOW03H03UMD70 | Tower System | 660
2023-03-15 | 2025-06-16 | 2025-06-22 | 80332498 | YR02 | Within 3 months | REL PCNF ACAS CSER NMAT PRC | RERP | Wi-Fi power cycle – Nacelle | WOW03C06UMD75 | Structure overall | 0
2023-03-08 | 2025-09-22 | 2025-09-28 | 80331937 | YR02 | Within a year | CRTD ACAS NMAT PRC | CRTD | C05 no Wi-Fi in nacelle | WOW03C05 | Wind Turbine C05_MHIV V164 MK1A 8.0 | 0
2023-02-23 | 2025-06-02 | 2025-06-08 | 80330914 | YR02 | Within 1 month | REL PCNF ACAS CSER MACM PRC | RERP | TCM(b), M-System | WOW03G04 | Wind Turbine G04_MHIV V164 MK1A 8.0 | 70544.04
2023-02-08 | 2025-08-18 | 2025-08-24 | 80328810 | YR02 | Within a year | REL ACAS CSER MACM PRC | RERP | Tetra battery swollen and repeater u/s | WOW03D02 | Wind Turbine D02_MHIV V164 MK1A 8.0 | 660
2023-02-07 | 2025-02-25 | 2025-03-03 | 80328746 | YR02 | Within 1 month | REL ACAS CSER GMPS MACM PRC | RERP MATR | WOW03 Sub cisco | WOW03Z03 | Off-shore substation Z03 | 17794.98
2023-02-06 | 2025-08-18 | 2025-08-24 | 80328684 | YR02 | Within 3 months | REL ACAS CSER NMAT PRC | RERP | F05 stop start stickers missing from hyd | WOW03F05 | Wind Turbine F05_MHIV V164 MK1A 8.0 | 0
2023-02-02 | 2025-02-25 | 2025-03-03 | 80328435 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | Vestas server panel alarms | WOW03X01CBA01UH001 | Wind Farm Server Panel - MVOW | 10560
2023-02-02 | 2025-02-25 | 2025-03-03 | 80328438 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | 34kV drawings incorrect on DORECO | WOW03Z03AAF | MEDIUM VOLTAGE DISTRIBUTION 34kV | 0
2023-02-02 | 2025-02-25 | 2025-03-03 | 80328439 | YR02 | Within 3 months | CRTD ACAS CSER NMAT PRC | CRTD | Alstom C264 bay - alarms won’t clear. | WOW03Z03AA | ELECTRICAL GRID AND DISTRIBUTION SYSTEMS | 0
2023-01-31 | 2025-06-09 | 2025-06-15 | 80328287 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | CMM(2808), V164 Consec. GenSide Brkr Ins | WOW03C02MSE | Inverter system | 72843.72
2023-01-31 | 2025-06-23 | 2025-06-29 | 80328416 | YR02 | Within 3 months | CRTD ACAS MACM PRC | CRTD | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03A05MSE | Inverter system | 77754.12
2023-01-30 | 2025-04-28 | 2025-05-04 | 80328100 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP MATR | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03B01 | Wind Turbine B01_MHIV V164 MK1A 8.0 | 77241.55
2023-01-29 | 2025-08-11 | 2025-08-17 | 80327839 | YR02 | Within 3 months | REL PCNF ACAS CSER MACM PRC | RERP | Aviation equipment error | WOW03H02 | Wind Turbine H02_MHIV V164 MK1A 8.0 | 73652.06
2023-01-23 | 2025-05-26 | 2025-06-01 | 80327481 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Rag and ratchet left under grid choke | WOW03C07MSE71TA001-RA001 | Choke | 1320
2023-01-17 | 2025-08-18 | 2025-08-24 | 80326863 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03F03MSE | Inverter system | 72474.12
2023-01-17 | 2025-04-07 | 2025-04-13 | 80327083 | YR02 | Within 3 months | REL ACAS MACM PRC | RERP | TCM(b), GbxA1Pln1-A | WOW03D03 | Wind Turbine D03_MHIV V164 MK1A 8.0 | 5978.25
2023-01-16 | 2025-09-29 | 2025-10-05 | 80326586 | YR02 | Within 1 month | REL ACAS PRC | RERP | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03D05 | Wind Turbine D05_MHIV V164 MK1A 8.0 | 5280
2023-01-16 | 2025-05-26 | 2025-06-01 | 80326590 | YR02 | Within 1 month | CRTD ACAS MACM PRC | CRTD | CMM(2808), V164 Consec. GenSide Brkr Ins | WOW03C07MSE | Inverter system | 78171.91
2023-01-12 | 2025-02-25 | 2025-03-03 | 80325623 | YR02 | Within 1 month | REL ACAS NMAT PRC | RERP | WOW0304 OnSS Gateway access issues visit | WOW03X01 | Onshore Substation =X01 | 2640
2023-01-06 | 2025-04-14 | 2025-04-20 | 80324795 | YR02 |  | CRTD ACAS NMAT PRC | CRTD | TCM(b), GbxBCrRe-R | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 2640
2023-01-06 | 2025-06-23 | 2025-06-29 | 80324817 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | TCM(b), Oil debris sensors | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 5599.56
2023-01-06 | 2025-04-14 | 2025-04-20 | 80324818 | YR02 |  | CRTD ACAS CSER MACM PRC | CRTD | TCM(b), GbxA2Pln3-R | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 0
2023-01-05 | 2025-05-19 | 2025-05-25 | 80324715 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | Aviation equipment error | WOW03C01XSD50 | Aviation signalling nacelle | 63843.5
2023-01-04 | 2025-08-25 | 2025-08-31 | 80324653 | YR02 | Within 1 month | REL PCNF ACAS MACM PRC | RERP | Aviation equipment error | WOW03G01XSD50 | Aviation signalling nacelle | 76292.06
2022-12-31 | 2025-05-26 | 2025-06-01 | 80323788 | YR02 | Within 1 month | REL ACAS CSER PRC | RERP | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 0
2022-12-30 | 2025-06-23 | 2025-06-29 | 80323726 | YR02 | Within a year | CRTD ACAS NMAT PRC | REPL | Nacelle Tool Replenishment | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 330
2022-12-30 | 2025-04-14 | 2025-04-20 | 80323748 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | Nacelle Tool Replenishment | WOW03E01 | Wind Turbine E01_MHIV V164 MK1A 8.0 | 0
2022-12-30 | 2024-10-29 | 2024-11-04 | 80323758 | YR02 | Within a year | CRTD ACAS NMAT PRC | COMP | Nacelle Tool Replenishment | WOW03G03 | Wind Turbine G03_MHIV V164 MK1A 8.0 | 425
2022-12-30 | 2025-04-07 | 2025-04-13 | 80323763 | YR02 | Within a year | REL ACAS NMAT PRC | RERP | Nacelle Tool Replenishment | WOW03H04 | Wind Turbine H04_MHIV V164 MK1A 8.0 | 330
2022-12-28 | 2025-06-02 | 2025-06-08 | 80321555 | YR02 | Within 1 month | REL ACAS CSER PRC | RERP | CMM(2806), V164 Consec. LineSide Brkr Fa | WOW03G03MSE | Inverter system | 0
2022-12-24 | 2025-06-09 | 2025-06-15 | 80321414 | YR02 | Within 1 month | REL ACAS MACM PRC | RERP | C02 Aviation light | WOW03C02XSD50EF001 | Aviation light installation | 49246.29
2022-12-24 | 2025-07-28 | 2025-08-03 | 80321533 | YR02 | Within 1 month | REL PCNF ACAS GMPS MACM PRC | RERP | F05 aviation light | WOW03F05XSD50EF001 | Aviation light installation | 51969.92
2022-12-23 | 2025-05-26 | 2025-06-01 | 80321412 | YR02 | Within 1 month | REL ACAS CSER MACM PRC | RERP | TCM(b), M-System Hub | WOW03C04 | Wind Turbine C04_MHIV V164 MK1A 8.0 | 70544.04
2022-12-18 | 2025-06-16 | 2025-06-22 | 80320518 | YR02 |  | REL ACAS MACM PRC | RERP | TCM(b), Oil debris sensors | WOW03C06 | Wind Turbine C06_MHIV V164 MK1A 8.0 | 3413.13
2022-12-17 | 2025-06-23 | 2025-06-29 | 80320410 | YR02 | Within a week | REL ACAS PRC | RERP | TCM(a), M-System | WOW03A01 | Wind Turbine A01_MHIV V164 MK1A 8.0 | 1320
2022-12-13 | 2025-04-07 | 2025-04-13 | 80320072 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03B04AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-05-26 | 2025-06-01 | 80320077 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03C04AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-06-16 | 2025-06-22 | 80320079 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03C06AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-04-07 | 2025-04-13 | 80320123 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | HV - enable remote access to REF 615 | WOW03D03AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-06-16 | 2025-06-22 | 80320129 | YR02 | Within a year | CRTD ACAS CSER NMAT PRC | CRTD | HV - enable remote access to REF 615 | WOW03E04AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-09-01 | 2025-09-07 | 80320137 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03G03AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-06-30 | 2025-07-06 | 80320139 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03H01AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-05-12 | 2025-05-18 | 80320141 | YR02 | Within a year | REL ACAS CSER NMAT PRC | REPL | HV - enable remote access to REF 615 | WOW03H03AAF80 | Switchgear >30kV-60 kV | 0
2022-12-13 | 2025-06-09 | 2025-06-15 | 80320143 | YR02 | Within a year | REL ACAS CSER NMAT PRC | RERP | HV - enable remote access to REF 615 | WOW03H05AAF80 | Switchgear >30kV-60 kV | 0
2022-11-24 | 2025-02-25 | 2025-03-03 | 80316105 | YR02 | Within 3 months | REL PCNF ACAS NMAT PRC | RERP | Rittal panel - faulty handle | WOW03X01YCA | Backbone network | 5280
2022-09-30 | 2025-02-25 | 2025-03-03 | 80307758 | YR02 | Within 1 month | REL ACAS CSER NMAT PRC | RERP | C264 (AAF24) Relay settings check | WOW03Z03 | Off-shore substation Z03 | 0
2022-08-17 | 2025-02-25 | 2025-03-03 | 80303930 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Issues with WOW03/04 DS agile alarms | WOW03X01 | Onshore Substation =X01 | 0
2022-08-17 | 2025-02-25 | 2025-03-03 | 80303931 | YR02 | Within 1 month | CRTD ACAS NMAT PRC | CRTD | Meter Access checks | WOW03X01 | Onshore Substation =X01 | 0
2022-05-27 | 2025-04-07 | 2025-04-13 | 80295599 | YR02 | Within three months | CRTD ACAS CSER MACM PRC | CRTD | TP tetra battries require replacing | WOW03D03YAB01UH002 | UPS_Panel | 0
2022-04-28 | 2025-09-08 | 2025-09-14 | 80291698 | YR02 | Within two months | REL ACAS CSER MACM PRC | RERP | Davit top cover requires replacing | WOW03H05XMM80GM001-UM001 | Crane Unit (Main Boom & Pedestall) | 3118.99
2022-04-24 | 2025-06-02 | 2025-06-08 | 80291098 | YR02 | Within three months | REL ACAS CSER MACM PRC | RERP | Davit top cover requires replacing | WOW03G03XMM80GM001-UM001 | Crane Unit (Main Boom & Pedestall) | 3118.99
2021-03-08 | 2025-07-07 | 2025-07-13 | 80251472 | YR02 | Within two months | REL ACAS NMAT PRC | RERP | Davit Pendant Repair | WOW03E02UMD80 | Transition Piece_TP | 2640
2020-10-02 | 2025-07-21 | 2025-07-27 | 80235942 | YR02 | Within six months | REL ACAS NMAT PRC | RERP | C06 Davit Slew cover broken | WOW03C06XMM80 | Service Crane TP | 3960